## Executive Summary
Complete GitFlow Migration & CI/CD Implementation Plan
Comprehensive End-to-End Delivery Plan with Dependencies
PROJECT OVERVIEW
Total Tasks: | 134
Total Estimated Hours: | 995 | (124.4 days @ 8hrs/day)
CI/CD Foundation Tasks: | 35
GitFlow Migration Tasks: | 99
EXECUTION ORDER & PHASE BREAKDOWN
# | Phase | Source | Tasks | Hours
1 | Phase 1: Foundation & Governance Setup | CI/CD Foundation | 8 | 12
2 | Phase 1: Quality Gates | GitFlow Migration | 15 | 238
3 | Phase 2: CI Pipeline - Quality Gates | CI/CD Foundation | 12 | 39
4 | Phase 2: Branching Migration | GitFlow Migration | 15 | 98
5 | Phase 3: CI/CD Transform | GitFlow Migration | 14 | 126
6 | Phase 3: CD Pipeline - Environment Gates | CI/CD Foundation | 10 | 23
7 | Phase 4: Database Strategy | GitFlow Migration | 12 | 56
8 | Special: Feature Flags | GitFlow Migration | 13 | 131
9 | Phase 5: Testing & Validation | GitFlow Migration | 15 | 96
10 | Phase 6: Rollout | GitFlow Migration | 15 | 157
11 | Phase 4: Validation, Rollback & Documentation | CI/CD Foundation | 5 | 19

## Complete Implementation Plan
Task ID | Source | Phase | Main Task | Sub-Task | Task Description | DRI | Hours | Complexity | Risk Level | Criticality | Prerequisites | Dependencies | Skills Required | Deliverable | Validation Checkpoint | Application Specifics | Status
>>> CI/CD Foundation: Phase 1: Foundation & Governance Setup
T001 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 1. Tool & License Verification | 1.1. Confirm SonarCloud paid license | 1.1. Confirm SonarCloud paid license | InfoSec | 1 | Low | Low | High | None | None | InfoSec, Procurement | SonarCloud license confirmation |  | Cross-Application | Not Started
T002 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 1. Tool & License Verification | 1.2. Confirm Snyk license/access | 1.2. Confirm Snyk license/access | InfoSec | 1 | Low | Low | High | None | None | InfoSec, Procurement | Snyk access key |  | Cross-Application | Not Started
T003 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 1. Tool & License Verification | 1.3. Confirm Datadog API keys | 1.3. Confirm Datadog API keys | SRE | 1 | Low | Low | High | None | None | SRE, Monitoring | Datadog API key |  | Cross-Application | Not Started
T004 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 2. Azure DevOps Integration | 2.1. Create SonarCloud Service Connection | 2.1. Create SonarCloud Service Connection | DevOps | 2 | Medium | Medium | High | 1.1 | 1.1 | DevOps, Azure DevOps Admin | SonarCloud service connection |  | Cross-Application | Not Started
T005 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 2. Azure DevOps Integration | 2.2. Create Snyk Service Connection | 2.2. Create Snyk Service Connection | DevOps | 1 | Medium | Medium | High | 1.2 | 1.2 | DevOps, Azure DevOps Admin | Snyk service connection |  | Cross-Application | Not Started
T006 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 2. Azure DevOps Integration | 2.3. Define security groups for approvals | 2.3. Define security groups for approvals | DevOps | 2 | Low | Low | High | None | None | DevOps, Azure DevOps Admin | Security groups and roles |  | Cross-Application | Not Started
T007 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 3. Central GitFlow Enforcement | 3.1. Enforce PR policies on develop branch | 3.1. Enforce PR policies on develop branch | DevOps | 3 | Medium | Medium | High | 2.3 | 2.3 | DevOps, Git, Azure DevOps | PR policies enforced |  | Cross-Application - All Repos | Not Started
T008 | CI/CD Foundation | Phase 1: Foundation & Governance Setup | 3. Central GitFlow Enforcement | 3.2. Define mandatory External Status Checks | 3.2. Define mandatory External Status Checks | DevOps | 1 | Medium | Low | High | 2.1, 2.2, 3.1 | 2.1, 2.2, 3.1 | DevOps, Azure DevOps | Status check policies |  | Cross-Application | Not Started
>>> GitFlow Migration: Phase 1: Quality Gates
T009 | GitFlow Migration | Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1 ACR & Artifact Repo Setup (Consolidated) | Combined tasks: Configure ACR retention policy; Setup ACR geo-replication (optional); Configure Artifact Feed retention | DevOps | 7 | Medium | Low | Low | ACR already exists | Previous phase tasks | Azure admin, DevOps | Combined: Geo-replication enabled, Retention configured, Retention policy configured |  | All applications | Not Started
T010 | GitFlow Migration | Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1 ACR & Artifact Repo Setup (Consolidated) | Combined tasks: Document artifact versioning strategy; Test ACR artifact retrieval; Test Artifact Feed retrieval | DevOps | 6 | Low | Low | High | None | Previous phase tasks | DevOps, Tech Lead | Combined: Versioning doc, Test results |  | All applications | Not Started
T011 | GitFlow Migration | Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2 API Versioning & BODE Prep (Consolidated) | Combined tasks: Review API containerization; Implement GitVersion for APIs; Tag API images with version+SHA | DevOps | 7 | Medium | Low | High | APIs containerized | Previous phase tasks | DevOps | Combined: GitVersion configured, API inventory, Images tagged correctly |  | All applications | Not Started
T012 | GitFlow Migration | Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2 API Versioning & BODE Prep (Consolidated) | Combined tasks: Test API BODE deployment; Document API BODE process | DevOps | 5 | Medium | Medium | Medium | 1.2.3 | Previous phase tasks | DevOps | Combined: API BODE doc, BODE verified for APIs |  | All applications | Not Started
T013 | GitFlow Migration | Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3 Web App BODE Preparation (Consolidated) | Combined tasks: Audit Web app configurations; Separate .env from build artifacts; Create config replacement script | DevOps | 14 | Medium | Medium | High | None | Previous phase tasks | DevOps, Frontend Dev | Combined: Config externalized, Replacement script, Config inventory |  | All applications | Not Started
T014 | GitFlow Migration | Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3 Web App BODE Preparation (Consolidated) | Combined tasks: Update Web build pipeline; Test Web BODE deployment; Document Web BODE process | DevOps | 11 | Medium | Medium | Medium | 1.3.2 | Previous phase tasks | DevOps, Frontend Dev | Combined: Pipeline updated, Web BODE doc, BODE verified for Web |  | All applications | Not Started
T015 | GitFlow Migration | Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4 Mobile App BODE Preparation (Consolidated) | Combined tasks: Audit Mobile app configurations; Separate config from build; Implement runtime config loading | DevOps | 18 | Medium | Medium | High | None | Previous phase tasks | DevOps, Mobile Dev | Combined: Runtime config works, Config externalized, Config inventory |  | All applications | Not Started
T016 | GitFlow Migration | Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4 Mobile App BODE Preparation (Consolidated) | Combined tasks: Update Mobile build pipeline; Test Mobile BODE deployment; Document Mobile BODE process | DevOps | 13 | Medium | Medium | Medium | 1.4.3 | Previous phase tasks | DevOps, Mobile Dev, QA | Combined: Pipeline updated, BODE verified for Mobile, Mobile BODE doc |  | All applications | Not Started
T017 | GitFlow Migration | Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5 Code Coverage Gates (Consolidated) | Combined tasks: Audit current test coverage; Install Coverlet in test projects; Create coverlet.runsettings; +2 more | DevOps | 11 | Low | Low | Medium | None | Previous phase tasks | DevOps, Developer, Developers, QA Lead | Combined: Coverlet installed, runsettings file, Coverage baseline report |  | All applications | Not Started
T018 | GitFlow Migration | Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5 Code Coverage Gates (Consolidated) | Combined tasks: Set 70% coverage threshold; Increase test coverage (if needed); Configure branch policies; +1 more | DevOps | 24 | Medium | Low | High | 1.5.4 | Previous phase tasks | All Developers, DevOps, DevOps admin | Combined: Threshold enforced, Branch policy set, 70% coverage achieved |  | All applications | Not Started
T019 | GitFlow Migration | Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6 Linting Implementation (Consolidated) | Combined tasks: Configure EditorConfig; Add StyleCop Analyzers; Create custom ruleset; +1 more | DevOps | 33 | Medium | Low | Medium | None | Previous phase tasks | All Developers, Senior Dev, Tech Lead | Combined: StyleCop installed, Ruleset file, .editorconfig file |  | All applications | Not Started
T020 | GitFlow Migration | Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6 Linting Implementation (Consolidated) | Combined tasks: Add linting to Azure Pipelines; Setup frontend linting (if applicable); Configure pre-commit hooks; +1 more | DevOps | 9 | Low | Low | Medium | 1.6.4 | Previous phase tasks | DevOps, Frontend Dev, Senior Dev | Combined: Pre-commit hooks, Linting in pipeline, Frontend linting |  | All applications | Not Started
T021 | GitFlow Migration | Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7 SonarQube/SonarCloud Setup (Consolidated) | Combined tasks: Decide SonarQube vs SonarCloud; Create SonarCloud org (if cloud); Create projects in SonarCloud; +7 more | DevOps | 21 | Medium | Low | Medium | None | Previous phase tasks | DevOps, DevOps admin, QA Lead, Senior Dev, Tech Lead | Combined: Decision made, Projects created, Org created |  | All applications | Not Started
T022 | GitFlow Migration | Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8 SAST Scanning (Consolidated) | Combined tasks: Select SAST tool; Setup SAST tool account; Configure SAST scan in pipeline; +7 more | DevOps | 43 | Medium | Medium | Medium | None | Previous phase tasks | DevOps, Developers, Security, Tech Lead | Combined: SAST in pipeline, Account setup, Tool selected |  | All applications | Not Started
T023 | GitFlow Migration | Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9 Branch Protection Policies (Consolidated) | Combined tasks: Create CODEOWNERS file; Configure main branch protection; Configure develop branch protection; +6 more | DevOps | 16 | Low | Low | Medium | None | Previous phase tasks | DevOps, DevOps admin, Tech Lead | Combined: Develop protected, Main protected, CODEOWNERS file |  | All applications | Not Started
>>> CI/CD Foundation: Phase 2: CI Pipeline - Quality Gates
T024 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 4. CI Pipeline Base Creation | 4.1. Create base azure-pipelines.yml | 4.1. Create base azure-pipelines.yml | DevOps | 2 | Medium | Low | High | 3.1, 3.2 | 3.1, 3.2 | DevOps, YAML, Azure Pipelines | Base pipeline YAML files |  | Per Repo: API, React, Android | Not Started
T025 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 5. Linting & Build | 5.1. Implement Linting/Formatting verification | 5.1. Implement Linting/Formatting verification | Dev | 4 | Medium | Low | High | 4.1 | 4.1 | C#, React, Android, DevOps | Linting config & pipeline |  | C# (StyleCop), React (ESLint), Android (ktlint) | Not Started
T026 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 5. Linting & Build | 5.2. Configure Compilation/Build step | 5.2. Configure Compilation/Build step | Dev | 2 | Low | Low | High | 5.1 | 5.1 | C#, React, Android, Build Tools | Build step in pipeline |  | C# (dotnet), React (npm), Android (gradle) | Not Started
T027 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 6. Unit Test & Coverage Gate | 6.1. Configure Unit Test with Coverage | 6.1. Configure Unit Test with Coverage | Dev | 5 | Medium | Medium | High | 5.2 | 5.2 | C#, React, Android, Testing | Unit tests with coverage |  | C# (Coverlet), React (Jest), Android (JaCoCo) | Not Started
T028 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 6. Unit Test & Coverage Gate | 6.2. Publish test results to Azure DevOps | 6.2. Publish test results to Azure DevOps | DevOps | 2 | Low | Low | Medium | 6.1 | 6.1 | DevOps, Azure Pipelines | Published test results |  | All applications | Not Started
T029 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 7. Dependency Security (Snyk) | 7.1. Implement Snyk Scan task (SCA) | 7.1. Implement Snyk Scan task (SCA) | DevOps | 3 | Medium | Medium | High | 2.2, 6.1 | 2.2, 6.1 | DevOps, InfoSec, Snyk | Snyk scanning in pipeline |  | NuGet, npm, Gradle | Not Started
T030 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 7. Dependency Security (Snyk) | 7.2. Configure Snyk to fail on critical | 7.2. Configure Snyk to fail on critical | InfoSec | 1 | Low | High | High | 7.1 | 7.1 | InfoSec, Security Policy | Security failure gate |  | All applications | Not Started
T031 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 8. Code Quality Gate (SonarCloud) | 8.1. Implement SonarCloud tasks | 8.1. Implement SonarCloud tasks | DevOps | 3 | Medium | Medium | High | 2.1, 6.1 | 2.1, 6.1 | DevOps, SonarCloud | SonarCloud integration |  | All applications | Not Started
T032 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 8. Code Quality Gate (SonarCloud) | 8.2. Define mandatory Quality Gate | 8.2. Define mandatory Quality Gate | InfoSec | 5 | Medium | Medium | High | 8.1 | 8.1 | InfoSec, Code Quality | Quality gate thresholds |  | May vary by app type | Not Started
T033 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 8. Code Quality Gate (SonarCloud) | 8.3. Verify QG status to Azure DevOps PR | 8.3. Verify QG status to Azure DevOps PR | DevOps | 2 | Medium | Medium | High | 8.2, 3.2 | 8.2, 3.2 | DevOps, Azure, SonarCloud | PR status check integration |  | All applications | Not Started
T034 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 9. BODE Artifact Creation | 9.1. API: Dockerfile, build, push to ACR | 9.1. API: Dockerfile, build, push to ACR | DevOps | 5 | High | Medium | High | 5.2, 8.3 | 5.2, 8.3 | DevOps, Docker, ACR | Container image in ACR |  | API only | Not Started
T035 | CI/CD Foundation | Phase 2: CI Pipeline - Quality Gates | 9. BODE Artifact Creation | 9.2. React/Android: Package & publish | 9.2. React/Android: Package & publish | DevOps | 5 | High | Medium | High | 5.2, 8.3 | 5.2, 8.3 | DevOps, Azure Artifacts | Build artifacts published |  | React App, Android App | Not Started
>>> GitFlow Migration: Phase 2: Branching Migration
T036 | GitFlow Migration | Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Document current branch structure; Analyze dev-6.0.0 commits; Analyze intg commits | DevOps | 9 | Medium | Low | High | Phase 1 complete | Previous phase tasks | Tech Lead | Combined: Current structure doc, Dev analysis doc, Intg analysis doc |  | All applications | Not Started
T037 | GitFlow Migration | Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Analyze qa commits; Analyze stage commits; Analyze main (prod) state | DevOps | 8 | Medium | Low | High | 2.1.3 | Previous phase tasks | Tech Lead | Combined: QA analysis doc, Stage analysis doc, Main state doc |  | All applications | Not Started
T038 | GitFlow Migration | Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Create GitFlow mapping plan; Identify work to preserve; Create rollback plan | DevOps | 10 | Medium | Medium | High | 2.1.2-2.1.6 | Previous phase tasks | DevOps, Senior Dev, Tech Lead | Combined: Rollback plan, Preservation checklist, Migration plan doc |  | All applications | Not Started
T039 | GitFlow Migration | Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | Get migration approval | Present plan to leadership | DevOps | 2 | Low | Low | Critical | 2.1.7-2.1.9 | Previous phase tasks | Tech Lead | Approval received |  | All applications | Not Started
T040 | GitFlow Migration | Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Announce code freeze; Create backup tags; Export current branch state; +1 more | DevOps | 4 | Low | Low | High | 2.1.10 | Previous phase tasks | Tech Lead | Combined: State exported, Announcement sent, Backup tags created |  | All applications | Not Started
T041 | GitFlow Migration | Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Merge dev-6.0.0 to develop; Cherry-pick unique intg commits; Cherry-pick unique qa commits; +1 more | DevOps | 9 | Medium | Medium | High | 2.2.4, 2.1.8 | Previous phase tasks | Tech Lead | Combined: Intg work preserved, QA work preserved, Dev work in develop |  | All applications | Not Started
T042 | GitFlow Migration | Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Verify all work preserved; Create initial release branch (if needed); Set develop as default branch; +1 more | DevOps | 6 | Low | Medium | Medium | 2.2.8 | Previous phase tasks | DevOps admin, Release Manager, Senior Dev, Tech Lead | Combined: Default changed, Release branch created, Verification passed |  | All applications | Not Started
T043 | GitFlow Migration | Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Apply branch protection policies; Test new branch structure | DevOps | 3 | Low | Low | Critical | 2.2.12, 1.9 complete | Previous phase tasks | DevOps admin, Developer | Combined: Policies applied, Test successful |  | All applications | Not Started
T044 | GitFlow Migration | Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Create GitFlow overview document; Document feature branch workflow; Document bugfix workflow; +1 more | DevOps | 11 | Low | Low | High | 2.2.14 | Previous phase tasks | Release Mgr, Tech Lead | Combined: Overview doc, Bugfix workflow doc, Feature workflow doc |  | All applications | Not Started
T045 | GitFlow Migration | Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Document hotfix workflow; Create Git command cheat sheet; Create visual flow diagrams; +1 more | DevOps | 10 | Low | Low | Medium | 2.3.1 | Previous phase tasks | Tech Lead | Combined: Cheat sheet, Hotfix workflow doc, Flow diagrams |  | All applications | Not Started
T046 | GitFlow Migration | Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Create commit message guidelines; Create FAQ document; Setup Git hooks for branch naming; +1 more | DevOps | 10 | Medium | Low | Medium | None | Previous phase tasks | Senior Dev, Tech Lead | Combined: Git hooks ready, FAQ doc, Commit guidelines |  | All applications | Not Started
T047 | GitFlow Migration | Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | Update Confluence/Wiki | Update all documentation links | DevOps | 2 | Low | Low | Medium | 2.3.1-2.3.12 | Previous phase tasks | Tech Lead | Wiki updated |  | All applications | Not Started
T048 | GitFlow Migration | Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Rename dev-6.0.0 to deprecated/; Rename intg to deprecated/; Rename qa to deprecated/ | DevOps | 3 | Low | Low | High | 2.2.14 | Previous phase tasks | DevOps | Combined: Branch renamed |  | All applications | Not Started
T049 | GitFlow Migration | Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Rename stage to deprecated/; Update pipeline triggers; Communicate branch deprecation | DevOps | 4 | Low | Low | Medium | 2.4.3 | Previous phase tasks | DevOps, Tech Lead | Combined: Branch renamed, Pipelines updated, Communication sent |  | All applications | Not Started
T050 | GitFlow Migration | Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Monitor for old branch usage; Delete remote deprecated branches; Document decommissioning | DevOps | 7 | Low | Low | Medium | 2.4.6 | Previous phase tasks | DevOps | Combined: Decommission doc, Branches deleted, No usage detected |  | All applications | Not Started
>>> GitFlow Migration: Phase 3: CI/CD Transform
T051 | GitFlow Migration | Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Design build pipeline architecture; Create build-pipeline.yml; Add trigger configuration; +1 more | DevOps | 12 | Medium | Low | High | Phase 2 complete | Previous phase tasks | DevOps, Tech Lead | Combined: Build YAML created, Triggers configured, Architecture doc |  | All applications | Not Started
T052 | GitFlow Migration | Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add build stage; Add unit test stage; Add integration test stage; +1 more | DevOps | 7 | Low | Low | High | 3.1.2 | Previous phase tasks | DevOps | Combined: Unit test stage, Build stage added, Integration test stage |  | All applications | Not Started
T053 | GitFlow Migration | Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add SonarCloud stages; Add SAST scan stage; Add Docker build stage; +1 more | DevOps | 9 | Medium | Low | High | 3.1.5, 1.7 complete | Previous phase tasks | DevOps | Combined: Docker build stage, SAST stage, SonarCloud stages |  | All applications | Not Started
T054 | GitFlow Migration | Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add .dacpac build stage; Add .dacpac publish stage; Test build pipeline end-to-end | DevOps | 8 | Medium | Medium | Critical | 3.1.2 | Previous phase tasks | DevOps | Combined: .dacpac publish stage, .dacpac build stage, Build pipeline works |  | All applications | Not Started
T055 | GitFlow Migration | Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Design deployment architecture; Create deploy-pipeline.yml; Add environment parameters; +2 more | DevOps | 15 | Medium | Medium | High | 3.1.15 | Previous phase tasks | DevOps, Tech Lead | Combined: Deploy architecture doc, Deploy YAML created, Parameters added |  | All applications | Not Started
T056 | GitFlow Migration | Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Add .dacpac download stage; Add database backup stage; Add .dacpac deployment stage; +2 more | DevOps | 15 | Medium | Medium | High | 3.2.4, 1.1.6 | Previous phase tasks | DB Dev, DevOps | Combined: Backup stage added, .dacpac deploy stage, .dacpac download works |  | All applications | Not Started
T057 | GitFlow Migration | Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Add health check stage; Add smoke test stage; Add approval gates; +2 more | DevOps | 14 | Medium | Medium | Low | 3.2.9 | Previous phase tasks | DevOps, DevOps admin, QA | Combined: Approvals configured, Smoke test stage, Health check stage |  | All applications | Not Started
T058 | GitFlow Migration | Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Test deploy pipeline to DEV; Test deploy pipeline to QA; Test deploy pipeline to STG; +1 more | DevOps | 14 | Medium | Medium | High | 3.2.2-3.2.15 | Previous phase tasks | DevOps, Tech Lead | Combined: QA deploy successful, STG deploy successful, DEV deploy successful |  | All applications | Not Started
T059 | GitFlow Migration | Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Create service principals for pipelines; Configure Key Vault integration | DevOps | 6 | Medium | Medium | High | None | Previous phase tasks | DevOps, Security | Combined: SPs created, Key Vault configured |  | All applications | Not Started
T060 | GitFlow Migration | Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Setup RBAC for environments; Configure pipeline permissions | DevOps | 5 | Medium | Medium | High | 3.3.1 | Previous phase tasks | DevOps, DevOps admin, Security | Combined: RBAC configured, Permissions set |  | All applications | Not Started
T061 | GitFlow Migration | Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Test security configuration; Document security setup | DevOps | 4 | Medium | Low | High | 3.3.1-3.3.4 | Previous phase tasks | DevOps, Security | Combined: Security doc, Security tested |  | All applications | Not Started
T062 | GitFlow Migration | Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Document build pipeline; Document deployment pipeline | DevOps | 7 | Low | Low | High | 3.1.15 | Previous phase tasks | DevOps | Combined: Build pipeline doc, Deploy pipeline doc |  | All applications | Not Started
T063 | GitFlow Migration | Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Document artifact selection; Create pipeline troubleshooting guide | DevOps | 5 | Low | Low | Medium | 3.2.4 | Previous phase tasks | DevOps | Combined: Troubleshooting guide, Artifact selection doc |  | All applications | Not Started
T064 | GitFlow Migration | Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Create pipeline architecture diagrams; Document environment variables | DevOps | 5 | Low | Low | Medium | 3.1.1, 3.2.1 | Previous phase tasks | DevOps | Combined: Architecture diagrams, Env var documentation |  | All applications | Not Started
>>> CI/CD Foundation: Phase 3: CD Pipeline - Environment Gates
T065 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 10. CD Pipeline Stage Definition | 10.1. Create multi-stage YAML pipeline | 10.1. Create multi-stage YAML pipeline | DevOps | 5 | High | Medium | High | 9.1, 9.2 | 9.1, 9.2 | DevOps, YAML, Pipelines | Multi-stage CD pipeline |  | Per application type | Not Started
T066 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 10. CD Pipeline Stage Definition | 10.2. Define Artifact Version parameter | 10.2. Define Artifact Version parameter | DevOps | 1 | Medium | Low | High | 10.1 | 10.1 | DevOps, Azure Pipelines | Artifact version parameter |  | All applications | Not Started
T067 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 11. DEV/INTEGRATION Gate | 11.1. Configure DEV/INTG deployment | 11.1. Configure DEV/INTG deployment | SRE | 2 | Medium | Low | High | 10.2 | 10.2 | SRE, DevOps, Infrastructure | DEV/INTG config |  | All applications | Not Started
T068 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 11. DEV/INTEGRATION Gate | 11.2. Implement Automated Smoke Tests | 11.2. Implement Automated Smoke Tests | Dev | 5 | Medium | Medium | High | 11.1 | 11.1 | Dev, Testing, API Testing | Smoke test suite |  | API (200), App (loads login) | Not Started
T069 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 12. QA Gate (Business Sign-off) | 12.1. Configure QA Pre-Deployment Approval | 12.1. Configure QA Pre-Deployment Approval | DevOps | 1 | Low | Low | High | 11.2, 2.3 | 11.2, 2.3 | DevOps, Azure Pipelines | QA approval gate |  | All applications | Not Started
T070 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 12. QA Gate (Business Sign-off) | 12.2. QA executes E2E/business tests | 12.2. QA executes E2E/business tests | QA Lead | 0 | High | Medium | High | 12.1 | 12.1 | QA, Manual Testing, E2E | QA test results |  | Duration varies by app | Not Started
T071 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 13. STAGE Gate (Observability) | 13.1. Implement Datadog Health Check | 13.1. Implement Datadog Health Check | SRE | 5 | High | Medium | High | 1.3, 12.2 | 1.3, 12.2 | SRE, Datadog API, Scripting | Health check gate |  | Error rate < 0.1% / 30 min | Not Started
T072 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 13. STAGE Gate (Observability) | 13.2. Configure RM Approval for STAGE | 13.2. Configure RM Approval for STAGE | DevOps | 1 | Low | Low | High | 13.1, 2.3 | 13.1, 2.3 | DevOps, Azure Pipelines | RM approval gate |  | All applications | Not Started
T073 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 14. PRODUCTION Gate | 14.1. Configure PROD Pre-Deployment | 14.1. Configure PROD Pre-Deployment | DevOps | 1 | Low | High | Critical | 13.2, 2.3 | 13.2, 2.3 | DevOps, Azure Pipelines | PROD approval gate |  | All applications | Not Started
T074 | CI/CD Foundation | Phase 3: CD Pipeline - Environment Gates | 14. PRODUCTION Gate | 14.2. Post-deployment Datadog Event | 14.2. Post-deployment Datadog Event | SRE | 2 | Medium | Low | Medium | 14.1, 1.3 | 14.1, 1.3 | SRE, Datadog API | Deployment event tracking |  | All applications | Not Started
>>> GitFlow Migration: Phase 4: Database Strategy
T075 | GitFlow Migration | Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Verify .dacpac artifact feed exists; Create .dacpac artifact feed (if needed) | DevOps | 3 | Low | Low | High | 1.1.3 | Previous phase tasks | DevOps | Combined: Status verified, Feed created |  | All applications | Not Started
T076 | GitFlow Migration | Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Configure .dacpac versioning; Test .dacpac publish | DevOps | 4 | Low | Low | High | 3.1.4, 4.1.1 | Previous phase tasks | DB Dev, DevOps | Combined: Publish tested, Versioning works |  | All applications | Not Started
T077 | GitFlow Migration | Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Test .dacpac download; Document .dacpac artifact strategy | DevOps | 4 | Low | Low | Medium | 4.1.4 | Previous phase tasks | DB Dev, DevOps | Combined: .dacpac strategy doc, Download tested |  | All applications | Not Started
T078 | GitFlow Migration | Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Verify Azure Storage exists; Create backup storage (if needed) | DevOps | 3 | Low | Low | High | None | Previous phase tasks | DevOps | Combined: Storage created, Storage verified |  | All applications | Not Started
T079 | GitFlow Migration | Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Create backup script; Integrate backup into deploy pipeline | DevOps | 5 | Medium | Low | Critical | 4.2.2 | Previous phase tasks | DB Developer, DevOps | Combined: Backup in pipeline, Backup script |  | All applications | Not Started
T080 | GitFlow Migration | Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Configure backup retention; Create restore script | DevOps | 5 | Medium | Medium | High | 4.2.2 | Previous phase tasks | DB Developer, DevOps | Combined: Retention configured, Restore script |  | All applications | Not Started
T081 | GitFlow Migration | Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Test backup in DEV; Test restore in DEV | DevOps | 5 | Medium | Low | High | 4.2.4 | Previous phase tasks | DB Dev, DB Developer, DevOps | Combined: Restore tested, Backup tested |  | All applications | Not Started
T082 | GitFlow Migration | Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Document backup/restore process; Train team on backup/restore | DevOps | 5 | Low | Low | High | 4.2.3-4.2.8 | Previous phase tasks | DB Developer | Combined: Backup runbook, Team trained |  | All applications | Not Started
T083 | GitFlow Migration | Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3 Rollback Testing (Consolidated) | Combined tasks: Create rollback decision tree; Test app-only rollback | DevOps | 5 | Low | Low | High | None | Previous phase tasks | DB Dev, DB Developer, DevOps, Tech Lead | Combined: App rollback tested, Decision tree |  | All applications | Not Started
T084 | GitFlow Migration | Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3 Rollback Testing (Consolidated) | Combined tasks: Test app + additive schema rollback; Test breaking schema scenario | DevOps | 6 | Medium | Medium | High | 4.2.8 | Previous phase tasks | DB Developer | Combined: Additive rollback tested, Breaking scenario tested |  | All applications | Not Started
T085 | GitFlow Migration | Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3 Rollback Testing (Consolidated) | Combined tasks: Measure rollback times; Create rollback runbook | DevOps | 6 | Low | Low | High | 4.3.2-4.3.4 | Previous phase tasks | DB Dev, DB Developer, DevOps | Combined: Timing report, Rollback runbook |  | All applications | Not Started
T086 | GitFlow Migration | Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3 Rollback Testing (Consolidated) | Combined tasks: Conduct rollback drill; Document lessons learned | DevOps | 5 | Low | Low | Medium | 4.3.6 | Previous phase tasks | All team, DB Developer | Combined: Lessons doc, Drill completed |  | All applications | Not Started
>>> GitFlow Migration: Special: Feature Flags
T087 | GitFlow Migration | Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Evaluate LaunchDarkly; Evaluate Split.io; Compare LaunchDarkly vs Split.io | DevOps | 11 | Medium | Low | High | None | Previous phase tasks | Senior Dev, Tech Lead | Combined: Comparison doc, Evaluation report |  | All applications | Not Started
T088 | GitFlow Migration | Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Get budget approval; Create tool account; Create projects in tool | DevOps | 6 | Low | Low | High | FF.1.3 | Previous phase tasks | DevOps, Management, Tech Lead | Combined: Projects created, Account created, Budget approved |  | All applications | Not Started
T089 | GitFlow Migration | Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Configure environments; Setup SDK keys; Configure access controls | DevOps | 6 | Low | Low | High | FF.1.6 | Previous phase tasks | DevOps, Security | Combined: SDK keys generated, Environments configured, Access controls set |  | All applications | Not Started
T090 | GitFlow Migration | Special: Feature Flags | FF.2 C# Adapter Development | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Design adapter architecture; Create IFeatureFlagProvider interface; Implement LaunchDarkly adapter | DevOps | 15 | Medium | Low | High | FF.1.5 | Previous phase tasks | Senior Dev, Tech Lead | Combined: Interface created, LD adapter complete, Architecture doc |  | All applications | Not Started
T091 | GitFlow Migration | Special: Feature Flags | FF.2 C# Adapter Development | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Implement Split.io adapter (optional); Implement InMemory adapter; Create FeatureFlagContext class | DevOps | 14 | Medium | Low | Medium | FF.2.2 | Previous phase tasks | Senior Dev | Combined: Split adapter complete, InMemory adapter complete, Context class created |  | All applications | Not Started
T092 | GitFlow Migration | Special: Feature Flags | FF.2 C# Adapter Development | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Implement DI configuration; Create helper extensions; Write unit tests for adapter | DevOps | 13 | Medium | Low | Medium | FF.2.3-FF.2.5 | Previous phase tasks | Senior Dev | Combined: DI configured, Tests written, Extensions created |  | All applications | Not Started
T093 | GitFlow Migration | Special: Feature Flags | FF.2 C# Adapter Development | Document adapter usage | Developer guide on using adapter | DevOps | 4 | Low | Low | High | FF.2.9 | Previous phase tasks | Senior Dev | Adapter guide |  | All applications | Not Started
T094 | GitFlow Migration | Special: Feature Flags | FF.3 Integration & Testing | FF.3 Integration & Testing (Consolidated) | Combined tasks: Add adapter to API projects; Add adapter to Web projects; Add adapter to Mobile projects (if applicable) | DevOps | 14 | Medium | Medium | Medium | FF.2.10 | Previous phase tasks | Developers, Frontend Devs, Mobile Devs | Combined: Mobile integrated, APIs integrated, Web integrated |  | All applications | Not Started
T095 | GitFlow Migration | Special: Feature Flags | FF.3 Integration & Testing | FF.3 Integration & Testing (Consolidated) | Combined tasks: Create test feature flags; Test flag evaluation; Test flag targeting | DevOps | 8 | Medium | Low | High | FF.3.1-FF.3.3 | Previous phase tasks | DevOps, Developers | Combined: Test flags created, Targeting tested, Evaluation tested |  | All applications | Not Started
T096 | GitFlow Migration | Special: Feature Flags | FF.3 Integration & Testing | FF.3 Integration & Testing (Consolidated) | Combined tasks: Test flag in all environments; Test adapter switching; Performance test flag evaluation | DevOps | 9 | Medium | Low | Medium | FF.3.5 | Previous phase tasks | DevOps, Developers, Senior Dev | Combined: All envs tested, Switching tested, Performance tested |  | All applications | Not Started
T097 | GitFlow Migration | Special: Feature Flags | FF.4 Documentation & Training | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create feature flag overview doc; Create flag lifecycle guide; Create flag naming conventions; +1 more | DevOps | 13 | Low | Low | High | FF.2.10 | Previous phase tasks | Senior Dev, Tech Lead | Combined: Overview doc, Lifecycle guide, Naming guide |  | All applications | Not Started
T098 | GitFlow Migration | Special: Feature Flags | FF.4 Documentation & Training | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create LaunchDarkly portal guide; Create code examples; Create training presentation; +1 more | DevOps | 13 | Low | Low | Medium | FF.1.7 | Previous phase tasks | DevOps, Senior Dev, Tech Lead | Combined: Training slides, Code examples, Portal guide |  | All applications | Not Started
T099 | GitFlow Migration | Special: Feature Flags | FF.4 Documentation & Training | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create FAQ for feature flags; Publish all flag documentation | DevOps | 5 | Low | Low | Medium | FF.4.8 | Previous phase tasks | Tech Lead | Combined: Flag FAQ, Docs published |  | All applications | Not Started
>>> GitFlow Migration: Phase 5: Testing & Validation
T100 | GitFlow Migration | Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Create test feature branch; Implement test feature; Create PR to develop; +1 more | DevOps | 8 | Low | Medium | High | Phase 3, 4 complete | Previous phase tasks | DevOps, Developer | Combined: Feature implemented, Branch created, PR created |  | All applications | Not Started
T101 | GitFlow Migration | Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Verify branch protection works; Complete PR review and merge; Verify build triggers on merge; +1 more | DevOps | 5 | Low | Low | High | 5.1.4 | Previous phase tasks | DevOps, Developer, Senior Dev | Combined: Protection verified, Build triggered, PR merged |  | All applications | Not Started
T102 | GitFlow Migration | Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Verify artifact versioning; Document dev branch test results | DevOps | 3 | Low | Low | High | 5.1.8 | Previous phase tasks | DevOps | Combined: Versions verified, Test report |  | All applications | Not Started
T103 | GitFlow Migration | Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Create test release branch; Update version in release; Trigger release build; +2 more | DevOps | 7 | Low | Medium | High | 5.1.10 | Previous phase tasks | DevOps, Release Manager | Combined: Release created, Build triggered, Version updated |  | All applications | Not Started
T104 | GitFlow Migration | Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Verify artifact selection works; Test QA approval gate; Deploy release to STG; +2 more | DevOps | 7 | Low | Medium | High | 5.2.5 | Previous phase tasks | DevOps, Release Manager, Tech Lead | Combined: Artifact verified, Approval tested, Deployed to STG |  | All applications | Not Started
T105 | GitFlow Migration | Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Deploy to PROD; Verify BODE in release; Merge release back to develop; +1 more | DevOps | 8 | Medium | Low | High | 5.2.10 | Previous phase tasks | DevOps, Release Manager | Combined: Deployed to PROD, BODE verified, Merged to develop |  | All applications | Not Started
T106 | GitFlow Migration | Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Simulate production bug; Create hotfix branch; Implement hotfix; +1 more | DevOps | 5 | Low | Low | High | 5.2.14 | Previous phase tasks | Developer, Tech Lead | Combined: Hotfix created, Bug scenario ready, Fix implemented |  | All applications | Not Started
T107 | GitFlow Migration | Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Expedited review; Merge hotfix to main; Verify hotfix build; +1 more | DevOps | 5 | Medium | Low | Critical | 5.3.4 | Previous phase tasks | DevOps, Developer, Senior Dev | Combined: Build successful, Merged to main, PR approved |  | All applications | Not Started
T108 | GitFlow Migration | Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Verify hotfix works; Merge hotfix to develop; Measure hotfix time; +1 more | DevOps | 5 | Low | Low | High | 5.3.8 | Previous phase tasks | Developer, QA, Tech Lead | Combined: Time measured, Fix verified, Merged to develop |  | All applications | Not Started
T109 | GitFlow Migration | Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Measure build pipeline time; Measure deploy to DEV time; Measure deploy to QA time; +1 more | DevOps | 5 | Low | Low | Medium | 5.1.10 | Previous phase tasks | DevOps | Combined: DEV deploy time, Build time measured, QA deploy time |  | All applications | Not Started
T110 | GitFlow Migration | Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Test concurrent feature builds; Measure rollback time; Measure DB restore time; +1 more | DevOps | 10 | Medium | Low | Medium | 5.1.10 | Previous phase tasks | DB Developer, DevOps | Combined: Rollback time measured, Restore time measured, Concurrent test done |  | All applications | Not Started
T111 | GitFlow Migration | Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Identify bottlenecks; Optimize slow stages; Document performance baselines | DevOps | 13 | Medium | Low | Medium | 5.4.1-5.4.8 | Previous phase tasks | DevOps | Combined: Optimizations complete, Baseline doc, Bottlenecks identified |  | All applications | Not Started
T112 | GitFlow Migration | Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5 Rollback Scenario Testing (Consolidated) | Combined tasks: Test rollback scenario 1; Test rollback scenario 2 | DevOps | 5 | Medium | Low | Critical | 4.3.2 | Previous phase tasks | DB Dev, DevOps | Combined: Scenario 2 tested, Scenario 1 tested |  | All applications | Not Started
T113 | GitFlow Migration | Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5 Rollback Scenario Testing (Consolidated) | Combined tasks: Test rollback scenario 3; Test rollback scenario 4 | DevOps | 7 | Medium | Medium | High | 4.3.4 | Previous phase tasks | DB Dev, DB Developer, DevOps | Combined: Scenario 3 tested, Scenario 4 tested |  | All applications | Not Started
T114 | GitFlow Migration | Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | Document all rollback scenarios | Complete rollback matrix | DevOps | 3 | Low | Low | Critical | 5.5.1-5.5.4 | Previous phase tasks | Tech Lead | Rollback matrix |  | All applications | Not Started
>>> GitFlow Migration: Phase 6: Rollout
T115 | GitFlow Migration | Phase 6: Rollout | 6.1 Documentation Preparation | 6.1 Documentation Preparation (Consolidated) | Combined tasks: Consolidate all documentation; Create quick start guide; Create video tutorials | DevOps | 12 | Medium | Low | Medium | Phase 5 complete | Previous phase tasks | Tech Lead | Combined: Quick start guide, Tutorial videos, Docs consolidated |  | All applications | Not Started
T116 | GitFlow Migration | Phase 6: Rollout | 6.1 Documentation Preparation | 6.1 Documentation Preparation (Consolidated) | Combined tasks: Create FAQ document; Update Confluence/Wiki; Create training slides | DevOps | 11 | Low | Low | High | 6.1.1 | Previous phase tasks | Tech Lead | Combined: Wiki updated, Training slides, FAQ doc |  | All applications | Not Started
T117 | GitFlow Migration | Phase 6: Rollout | 6.1 Documentation Preparation | Share documentation links | Send to all developers | DevOps | 1 | Low | Low | High | 6.1.5 | Previous phase tasks | Tech Lead | Links shared |  | All applications | Not Started
T118 | GitFlow Migration | Phase 6: Rollout | 6.2 Team Training | 6.2 Team Training (Consolidated) | Combined tasks: Schedule training sessions; Conduct training session 1 | DevOps | 4 | Low | Low | High | 6.1.7 | Previous phase tasks | Tech Lead | Combined: Session 1 complete, Sessions scheduled |  | All applications | Not Started
T119 | GitFlow Migration | Phase 6: Rollout | 6.2 Team Training | 6.2 Team Training (Consolidated) | Combined tasks: Conduct training session 2; Conduct hands-on workshop | DevOps | 4 | Low | Low | High | 6.2.2 | Previous phase tasks | DevOps, Senior Dev, Tech Lead | Combined: Session 2 complete, Workshop complete |  | All applications | Not Started
T120 | GitFlow Migration | Phase 6: Rollout | 6.2 Team Training | 6.2 Team Training (Consolidated) | Combined tasks: Office hours - Week 1; Gather training feedback | DevOps | 6 | Low | Low | Medium | 6.2.4 | Previous phase tasks | Tech Lead | Combined: Office hours done, Feedback collected |  | All applications | Not Started
T121 | GitFlow Migration | Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Select pilot team; Pilot team kickoff; Migrate pilot repositories | DevOps | 6 | Medium | Medium | High | 6.2.6 | Previous phase tasks | DevOps, Tech Lead | Combined: Pilot team selected, Kickoff complete, Repos migrated |  | All applications | Not Started
T122 | GitFlow Migration | Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Shadow pilot team - Day 1; Shadow pilot team - Week 1; Gather pilot feedback | DevOps | 20 | Low | Low | High | 6.3.3 | Previous phase tasks | DevOps, Tech Lead | Combined: Week 1 complete, Feedback collected, Day 1 support done |  | All applications | Not Started
T123 | GitFlow Migration | Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Address pilot issues; Update documentation from pilot; Pilot go/no-go decision | DevOps | 12 | Medium | Low | High | 6.3.6 | Previous phase tasks | DevOps, Management, Tech Lead | Combined: Docs updated, Decision made, Issues resolved |  | All applications | Not Started
T124 | GitFlow Migration | Phase 6: Rollout | 6.4 Full Team Rollout | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Create rollout schedule; Migrate Team A; Support Team A - Week 1 | DevOps | 13 | Medium | Medium | High | 6.3.9 | Previous phase tasks | DevOps, Tech Lead | Combined: Team A support done, Schedule created, Team A migrated |  | All applications | Not Started
T125 | GitFlow Migration | Phase 6: Rollout | 6.4 Full Team Rollout | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Migrate Team B; Support Team B - Week 1; Migrate Team C | DevOps | 17 | Medium | Medium | High | 6.4.2 | Previous phase tasks | DevOps, Tech Lead | Combined: Team B migrated, Team B support done, Team C migrated |  | All applications | Not Started
T126 | GitFlow Migration | Phase 6: Rollout | 6.4 Full Team Rollout | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Support Team C - Week 1; Migrate remaining teams; Extended support period | DevOps | 27 | Medium | Medium | High | 6.4.6 | Previous phase tasks | DevOps, Tech Lead | Combined: Support period complete, All teams migrated, Team C support done |  | All applications | Not Started
T127 | GitFlow Migration | Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Verify all teams migrated; Archive old pipeline definitions; Disable old pipelines; +1 more | DevOps | 7 | Low | Low | Medium | 6.4.9 | Previous phase tasks | DevOps, Tech Lead | Combined: All teams confirmed, Pipelines archived, Old pipelines disabled |  | All applications | Not Started
T128 | GitFlow Migration | Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Archive old documentation; Update all wiki links; Announce completion; +1 more | DevOps | 10 | Low | Low | Medium | 6.5.1 | Previous phase tasks | Tech Lead | Combined: Announcement sent, Docs archived, Links updated |  | All applications | Not Started
T129 | GitFlow Migration | Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Conduct retrospective; Create case study | DevOps | 7 | Low | Low | Low | 6.5.8 | Previous phase tasks | Tech Lead | Combined: Retro complete, Case study |  | All applications | Not Started
>>> CI/CD Foundation: Phase 4: Validation, Rollback & Documentation
T130 | CI/CD Foundation | Phase 4: Validation, Rollback & Documentation | 15. Rollback Testing (BODE) | 15.1. Deploy failing artifact to STAGE | 15.1. Deploy failing artifact to STAGE | DevOps | 2 | Medium | Medium | High | 14.2 | 14.2 | DevOps, Testing | Failed deployment test |  | All applications | Not Started
T131 | CI/CD Foundation | Phase 4: Validation, Rollback & Documentation | 15. Rollback Testing (BODE) | 15.2. Trigger Rollback to stable version | 15.2. Trigger Rollback to stable version | DevOps | 2 | Medium | Medium | High | 15.1, 10.2 | 15.1, 10.2 | DevOps, Rollback Procedures | Successful rollback |  | All applications | Not Started
T132 | CI/CD Foundation | Phase 4: Validation, Rollback & Documentation | 16. JIRA Traceability | 16.1. Integrate Azure DevOps to JIRA | 16.1. Integrate Azure DevOps to JIRA | DevOps | 5 | Medium | Low | Medium | 14.2 | 14.2 | DevOps, JIRA API | JIRA integration |  | All applications | Not Started
T133 | CI/CD Foundation | Phase 4: Validation, Rollback & Documentation | 17. Documentation & Handover | 17.1. Document CI/CD structure & rollback | 17.1. Document CI/CD structure & rollback | DevOps | 5 | Medium | Low | High | 15.2 | 15.2 | Technical Writing, DevOps | Complete CI/CD runbook |  | All applications | Not Started
T134 | CI/CD Foundation | Phase 4: Validation, Rollback & Documentation | 17. Documentation & Handover | 17.2. Training session for Dev teams | 17.2. Training session for Dev teams | DevOps | 5 | Low | Low | High | 17.1 | 17.1 | Training, DevOps | Team training completion |  | All teams | Not Started

## Dependency Map
Task Dependency & Execution Flow Validation
Task ID | Task Name | Prerequisites | Dependencies | Blocking Tasks | Status
T001 | 1.1. Confirm SonarCloud paid license | None | None | None | Not Started
T002 | 1.2. Confirm Snyk license/access | None | None | None | Not Started
T003 | 1.3. Confirm Datadog API keys | None | None | None | Not Started
T004 | 2.1. Create SonarCloud Service Connection | 1.1 | 1.1 | None | Not Started
T005 | 2.2. Create Snyk Service Connection | 1.2 | 1.2 | None | Not Started
T006 | 2.3. Define security groups for approvals | None | None | None | Not Started
T007 | 3.1. Enforce PR policies on develop branch | 2.3 | 2.3 | None | Not Started
T008 | 3.2. Define mandatory External Status Checks | 2.1, 2.2, 3.1 | 2.1, 2.2, 3.1 | None | Not Started
T009 | 1.1 ACR & Artifact Repo Setup (Consolidated) | ACR already exists | Previous phase tasks | None | Not Started
T010 | 1.1 ACR & Artifact Repo Setup (Consolidated) | None | Previous phase tasks | None | Not Started
T011 | 1.2 API Versioning & BODE Prep (Consolidated) | APIs containerized | Previous phase tasks | None | Not Started
T012 | 1.2 API Versioning & BODE Prep (Consolidated) | 1.2.3 | Previous phase tasks | None | Not Started
T013 | 1.3 Web App BODE Preparation (Consolidated) | None | Previous phase tasks | None | Not Started
T014 | 1.3 Web App BODE Preparation (Consolidated) | 1.3.2 | Previous phase tasks | None | Not Started
T015 | 1.4 Mobile App BODE Preparation (Consolidated) | None | Previous phase tasks | None | Not Started
T016 | 1.4 Mobile App BODE Preparation (Consolidated) | 1.4.3 | Previous phase tasks | None | Not Started
T017 | 1.5 Code Coverage Gates (Consolidated) | None | Previous phase tasks | None | Not Started
T018 | 1.5 Code Coverage Gates (Consolidated) | 1.5.4 | Previous phase tasks | None | Not Started
T019 | 1.6 Linting Implementation (Consolidated) | None | Previous phase tasks | None | Not Started
T020 | 1.6 Linting Implementation (Consolidated) | 1.6.4 | Previous phase tasks | None | Not Started
T021 | 1.7 SonarQube/SonarCloud Setup (Consolidated) | None | Previous phase tasks | None | Not Started
T022 | 1.8 SAST Scanning (Consolidated) | None | Previous phase tasks | None | Not Started
T023 | 1.9 Branch Protection Policies (Consolidated) | None | Previous phase tasks | None | Not Started
T024 | 4.1. Create base azure-pipelines.yml | 3.1, 3.2 | 3.1, 3.2 | None | Not Started
T025 | 5.1. Implement Linting/Formatting verification | 4.1 | 4.1 | None | Not Started
T026 | 5.2. Configure Compilation/Build step | 5.1 | 5.1 | None | Not Started
T027 | 6.1. Configure Unit Test with Coverage | 5.2 | 5.2 | None | Not Started
T028 | 6.2. Publish test results to Azure DevOps | 6.1 | 6.1 | None | Not Started
T029 | 7.1. Implement Snyk Scan task (SCA) | 2.2, 6.1 | 2.2, 6.1 | None | Not Started
T030 | 7.2. Configure Snyk to fail on critical | 7.1 | 7.1 | None | Not Started
T031 | 8.1. Implement SonarCloud tasks | 2.1, 6.1 | 2.1, 6.1 | None | Not Started
T032 | 8.2. Define mandatory Quality Gate | 8.1 | 8.1 | None | Not Started
T033 | 8.3. Verify QG status to Azure DevOps PR | 8.2, 3.2 | 8.2, 3.2 | None | Not Started
T034 | 9.1. API: Dockerfile, build, push to ACR | 5.2, 8.3 | 5.2, 8.3 | None | Not Started
T035 | 9.2. React/Android: Package & publish | 5.2, 8.3 | 5.2, 8.3 | None | Not Started
T036 | 2.1 Branch Mapping & Analysis (Consolidated) | Phase 1 complete | Previous phase tasks | None | Not Started
T037 | 2.1 Branch Mapping & Analysis (Consolidated) | 2.1.3 | Previous phase tasks | None | Not Started
T038 | 2.1 Branch Mapping & Analysis (Consolidated) | 2.1.2-2.1.6 | Previous phase tasks | None | Not Started
T039 | Get migration approval | 2.1.7-2.1.9 | Previous phase tasks | None | Not Started
T040 | 2.2 New Branch Structure Creation (Consolidated) | 2.1.10 | Previous phase tasks | None | Not Started
T041 | 2.2 New Branch Structure Creation (Consolidated) | 2.2.4, 2.1.8 | Previous phase tasks | None | Not Started
T042 | 2.2 New Branch Structure Creation (Consolidated) | 2.2.8 | Previous phase tasks | None | Not Started
T043 | 2.2 New Branch Structure Creation (Consolidated) | 2.2.12, 1.9 complete | Previous phase tasks | None | Not Started
T044 | 2.3 Developer Workflow Documentation (Consolidated) | 2.2.14 | Previous phase tasks | None | Not Started
T045 | 2.3 Developer Workflow Documentation (Consolidated) | 2.3.1 | Previous phase tasks | None | Not Started
T046 | 2.3 Developer Workflow Documentation (Consolidated) | None | Previous phase tasks | None | Not Started
T047 | Update Confluence/Wiki | 2.3.1-2.3.12 | Previous phase tasks | None | Not Started
T048 | 2.4 Old Branch Decommissioning (Consolidated) | 2.2.14 | Previous phase tasks | None | Not Started
T049 | 2.4 Old Branch Decommissioning (Consolidated) | 2.4.3 | Previous phase tasks | None | Not Started
T050 | 2.4 Old Branch Decommissioning (Consolidated) | 2.4.6 | Previous phase tasks | None | Not Started
T051 | 3.1 Build Pipeline Design & YAML (Consolidated) | Phase 2 complete | Previous phase tasks | None | Not Started
T052 | 3.1 Build Pipeline Design & YAML (Consolidated) | 3.1.2 | Previous phase tasks | None | Not Started
T053 | 3.1 Build Pipeline Design & YAML (Consolidated) | 3.1.5, 1.7 complete | Previous phase tasks | None | Not Started
T054 | 3.1 Build Pipeline Design & YAML (Consolidated) | 3.1.2 | Previous phase tasks | None | Not Started
T055 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | 3.1.15 | Previous phase tasks | None | Not Started
T056 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | 3.2.4, 1.1.6 | Previous phase tasks | None | Not Started
T057 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | 3.2.9 | Previous phase tasks | None | Not Started
T058 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | 3.2.2-3.2.15 | Previous phase tasks | None | Not Started
T059 | 3.3 Security & Access Setup (Consolidated) | None | Previous phase tasks | None | Not Started
T060 | 3.3 Security & Access Setup (Consolidated) | 3.3.1 | Previous phase tasks | None | Not Started
T061 | 3.3 Security & Access Setup (Consolidated) | 3.3.1-3.3.4 | Previous phase tasks | None | Not Started
T062 | 3.4 Pipeline Documentation (Consolidated) | 3.1.15 | Previous phase tasks | None | Not Started
T063 | 3.4 Pipeline Documentation (Consolidated) | 3.2.4 | Previous phase tasks | None | Not Started
T064 | 3.4 Pipeline Documentation (Consolidated) | 3.1.1, 3.2.1 | Previous phase tasks | None | Not Started
T065 | 10.1. Create multi-stage YAML pipeline | 9.1, 9.2 | 9.1, 9.2 | None | Not Started
T066 | 10.2. Define Artifact Version parameter | 10.1 | 10.1 | None | Not Started
T067 | 11.1. Configure DEV/INTG deployment | 10.2 | 10.2 | None | Not Started
T068 | 11.2. Implement Automated Smoke Tests | 11.1 | 11.1 | None | Not Started
T069 | 12.1. Configure QA Pre-Deployment Approval | 11.2, 2.3 | 11.2, 2.3 | None | Not Started
T070 | 12.2. QA executes E2E/business tests | 12.1 | 12.1 | None | Not Started
T071 | 13.1. Implement Datadog Health Check | 1.3, 12.2 | 1.3, 12.2 | None | Not Started
T072 | 13.2. Configure RM Approval for STAGE | 13.1, 2.3 | 13.1, 2.3 | None | Not Started
T073 | 14.1. Configure PROD Pre-Deployment | 13.2, 2.3 | 13.2, 2.3 | None | Not Started
T074 | 14.2. Post-deployment Datadog Event | 14.1, 1.3 | 14.1, 1.3 | None | Not Started
T075 | 4.1 .dacpac Artifact Management (Consolidated) | 1.1.3 | Previous phase tasks | None | Not Started
T076 | 4.1 .dacpac Artifact Management (Consolidated) | 3.1.4, 4.1.1 | Previous phase tasks | None | Not Started
T077 | 4.1 .dacpac Artifact Management (Consolidated) | 4.1.4 | Previous phase tasks | None | Not Started
T078 | 4.2 Database Backup & Restore (Consolidated) | None | Previous phase tasks | None | Not Started
T079 | 4.2 Database Backup & Restore (Consolidated) | 4.2.2 | Previous phase tasks | None | Not Started
T080 | 4.2 Database Backup & Restore (Consolidated) | 4.2.2 | Previous phase tasks | None | Not Started
T081 | 4.2 Database Backup & Restore (Consolidated) | 4.2.4 | Previous phase tasks | None | Not Started
T082 | 4.2 Database Backup & Restore (Consolidated) | 4.2.3-4.2.8 | Previous phase tasks | None | Not Started
T083 | 4.3 Rollback Testing (Consolidated) | None | Previous phase tasks | None | Not Started
T084 | 4.3 Rollback Testing (Consolidated) | 4.2.8 | Previous phase tasks | None | Not Started
T085 | 4.3 Rollback Testing (Consolidated) | 4.3.2-4.3.4 | Previous phase tasks | None | Not Started
T086 | 4.3 Rollback Testing (Consolidated) | 4.3.6 | Previous phase tasks | None | Not Started
T087 | FF.1 Tool Selection & Setup (Consolidated) | None | Previous phase tasks | None | Not Started
T088 | FF.1 Tool Selection & Setup (Consolidated) | FF.1.3 | Previous phase tasks | None | Not Started
T089 | FF.1 Tool Selection & Setup (Consolidated) | FF.1.6 | Previous phase tasks | None | Not Started
T090 | FF.2 C# Adapter Development (Consolidated) | FF.1.5 | Previous phase tasks | None | Not Started
T091 | FF.2 C# Adapter Development (Consolidated) | FF.2.2 | Previous phase tasks | None | Not Started
T092 | FF.2 C# Adapter Development (Consolidated) | FF.2.3-FF.2.5 | Previous phase tasks | None | Not Started
T093 | Document adapter usage | FF.2.9 | Previous phase tasks | None | Not Started
T094 | FF.3 Integration & Testing (Consolidated) | FF.2.10 | Previous phase tasks | None | Not Started
T095 | FF.3 Integration & Testing (Consolidated) | FF.3.1-FF.3.3 | Previous phase tasks | None | Not Started
T096 | FF.3 Integration & Testing (Consolidated) | FF.3.5 | Previous phase tasks | None | Not Started
T097 | FF.4 Documentation & Training (Consolidated) | FF.2.10 | Previous phase tasks | None | Not Started
T098 | FF.4 Documentation & Training (Consolidated) | FF.1.7 | Previous phase tasks | None | Not Started
T099 | FF.4 Documentation & Training (Consolidated) | FF.4.8 | Previous phase tasks | None | Not Started
T100 | 5.1 Development Branch Testing (Consolidated) | Phase 3, 4 complete | Previous phase tasks | None | Not Started
T101 | 5.1 Development Branch Testing (Consolidated) | 5.1.4 | Previous phase tasks | None | Not Started
T102 | 5.1 Development Branch Testing (Consolidated) | 5.1.8 | Previous phase tasks | None | Not Started
T103 | 5.2 Release Branch Testing (Consolidated) | 5.1.10 | Previous phase tasks | None | Not Started
T104 | 5.2 Release Branch Testing (Consolidated) | 5.2.5 | Previous phase tasks | None | Not Started
T105 | 5.2 Release Branch Testing (Consolidated) | 5.2.10 | Previous phase tasks | None | Not Started
T106 | 5.3 Hotfix Branch Testing (Consolidated) | 5.2.14 | Previous phase tasks | None | Not Started
T107 | 5.3 Hotfix Branch Testing (Consolidated) | 5.3.4 | Previous phase tasks | None | Not Started
T108 | 5.3 Hotfix Branch Testing (Consolidated) | 5.3.8 | Previous phase tasks | None | Not Started
T109 | 5.4 Performance & Load Testing (Consolidated) | 5.1.10 | Previous phase tasks | None | Not Started
T110 | 5.4 Performance & Load Testing (Consolidated) | 5.1.10 | Previous phase tasks | None | Not Started
T111 | 5.4 Performance & Load Testing (Consolidated) | 5.4.1-5.4.8 | Previous phase tasks | None | Not Started
T112 | 5.5 Rollback Scenario Testing (Consolidated) | 4.3.2 | Previous phase tasks | None | Not Started
T113 | 5.5 Rollback Scenario Testing (Consolidated) | 4.3.4 | Previous phase tasks | None | Not Started
T114 | Document all rollback scenarios | 5.5.1-5.5.4 | Previous phase tasks | None | Not Started
T115 | 6.1 Documentation Preparation (Consolidated) | Phase 5 complete | Previous phase tasks | None | Not Started
T116 | 6.1 Documentation Preparation (Consolidated) | 6.1.1 | Previous phase tasks | None | Not Started
T117 | Share documentation links | 6.1.5 | Previous phase tasks | None | Not Started
T118 | 6.2 Team Training (Consolidated) | 6.1.7 | Previous phase tasks | None | Not Started
T119 | 6.2 Team Training (Consolidated) | 6.2.2 | Previous phase tasks | None | Not Started
T120 | 6.2 Team Training (Consolidated) | 6.2.4 | Previous phase tasks | None | Not Started
T121 | 6.3 Pilot Team Rollout (Consolidated) | 6.2.6 | Previous phase tasks | None | Not Started
T122 | 6.3 Pilot Team Rollout (Consolidated) | 6.3.3 | Previous phase tasks | None | Not Started
T123 | 6.3 Pilot Team Rollout (Consolidated) | 6.3.6 | Previous phase tasks | None | Not Started
T124 | 6.4 Full Team Rollout (Consolidated) | 6.3.9 | Previous phase tasks | None | Not Started
T125 | 6.4 Full Team Rollout (Consolidated) | 6.4.2 | Previous phase tasks | None | Not Started
T126 | 6.4 Full Team Rollout (Consolidated) | 6.4.6 | Previous phase tasks | None | Not Started
T127 | 6.5 Old Process Decommissioning (Consolidated) | 6.4.9 | Previous phase tasks | None | Not Started
T128 | 6.5 Old Process Decommissioning (Consolidated) | 6.5.1 | Previous phase tasks | None | Not Started
T129 | 6.5 Old Process Decommissioning (Consolidated) | 6.5.8 | Previous phase tasks | None | Not Started
T130 | 15.1. Deploy failing artifact to STAGE | 14.2 | 14.2 | None | Not Started
T131 | 15.2. Trigger Rollback to stable version | 15.1, 10.2 | 15.1, 10.2 | None | Not Started
T132 | 16.1. Integrate Azure DevOps to JIRA | 14.2 | 14.2 | None | Not Started
T133 | 17.1. Document CI/CD structure & rollback | 15.2 | 15.2 | None | Not Started
T134 | 17.2. Training session for Dev teams | 17.1 | 17.1 | None | Not Started

## Validation Checklist
End-to-End Validation & Quality Checkpoints
Phase | Validation Point | Expected Outcome | Actual Result | Pass/Fail
Phase 1: Foundation | All licenses confirmed | SonarCloud, Snyk, Datadog access verified
Phase 1: Foundation | Service connections working | All Azure DevOps connections test successfully
Phase 1: Foundation | PR policies enforced | Direct commits to develop blocked
Phase 1: Quality Gates | ACR properly configured | Container images can be pushed/pulled
Phase 1: Quality Gates | All quality tools integrated | Linting, Coverage, SonarCloud, Snyk all running
Phase 2: CI Pipeline | Pipeline YAML files created | All repos have functional CI pipelines
Phase 2: CI Pipeline | Quality gates blocking PRs | Failed quality checks prevent merge
Phase 2: CI Pipeline | BODE artifacts created | Immutable artifacts in ACR/Azure Artifacts
Phase 2: Branching | GitFlow structure implemented | All branches created per GitFlow model
Phase 2: Branching | Branch protection active | Protected branches cannot be force-pushed
Phase 3: CI/CD Transform | Build pipelines functional | All applications build successfully
Phase 3: CI/CD Transform | Deploy pipelines functional | All applications deploy to DEV
Phase 3: CD Pipeline | Multi-stage pipeline works | Can deploy through all environments
Phase 3: CD Pipeline | Approval gates functional | Manual approvals required at each gate
Phase 3: CD Pipeline | Datadog health checks working | Automated health validation passes
Phase 4: Database | .dacpac deployment works | Database changes deploy successfully
Phase 4: Database | Rollback tested | Can rollback database changes
Feature Flags | Feature flag system operational | Can toggle features without deployment
Phase 5: Testing | All branch flows tested | Dev, release, hotfix flows validated
Phase 5: Testing | Performance acceptable | Load tests meet requirements
Phase 5: Testing | Integration tests pass | E2E scenarios work correctly
Phase 6: Rollout | Documentation complete | All runbooks and guides available
Phase 6: Rollout | Teams trained | All developers understand new process
Phase 4: Final Validation | Rollback proven | Can rollback to previous artifact
Phase 4: Final Validation | JIRA integration working | Deployments update JIRA tickets
Phase 4: Final Validation | Full end-to-end flow | Code commit → Production deployment works