## Summary
GitFlow Migration - Detailed Task Summary
Phase | Total Hours | Description
Phase 1: Quality Gates |  | ACR/Artifact setup, API/Web/Mobile BODE prep, Coverage, Linting, SonarCloud, SAST, Branch protection
Phase 2: Branching Migration |  | Branch mapping, new structure creation, developer documentation, old branch decommission
Phase 3: CI/CD Transform |  | Build pipeline YAML, deploy pipeline YAML, security setup, documentation
Phase 4: Database Strategy |  | .dacpac artifact management, backup/restore, rollback testing
Phase 5: Testing |  | Dev/Release/Hotfix branch testing, performance/load testing, rollback scenarios
Phase 6: Rollout |  | Documentation prep, team training, pilot rollout, full rollout, decommissioning
SPECIAL: Feature Flags |  | Tool selection, C# adapter development, integration, training
TOTAL HOURS
TOTAL DAYS (4.5 hrs/day) |  | Assuming 4-5 hours productive work per day
TOTAL WEEKS (5 days/week) |  | Calendar weeks required
Task Breakdown
Total Tasks |  | Total number of individual tasks
Critical Tasks |  | Tasks marked as Critical
High Risk Tasks |  | Tasks with High risk
High Complexity Tasks |  | Tasks with High complexity

## GitFlow Migration Tasks
Phase | Sub-Phase | Task ID | Task Name | Task Description | Hours | Complexity | Risk Level | Criticality | Prerequisites | Skills Required | Deliverable | Validation Required
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.1 | Configure ACR retention policy | Set 30-60 day retention policy for container images | 2 | Low | Low | High | ACR already exists | DevOps, Azure admin | Retention policy configured | Verify old images auto-delete
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.2 | Setup ACR geo-replication (optional) | Enable geo-replication for DR if needed | 3 | Medium | Low | Low | 1.1.1 | DevOps, Azure admin | Geo-replication enabled | Test failover
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.3 | Configure Artifact Feed retention | Set retention: 30 days dev, 60 days release, indefinite prod | 2 | Low | Low | High | Artifact Feed exists | DevOps | Retention configured | Old packages cleaned
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.4 | Document artifact versioning strategy | Define versioning: v{major}.{minor}.{patch}-{sha} | 2 | Low | Low | High | None | Tech Lead, DevOps | Versioning doc | Team review
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.5 | Test ACR artifact retrieval | Test pulling specific image versions by tag | 2 | Low | Low | High | 1.1.1 | DevOps | Test results | All envs can pull
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | 1.1.6 | Test Artifact Feed retrieval | Test downloading specific .dacpac versions | 2 | Low | Low | High | 1.1.3 | DevOps | Test results | Can download by version
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2.1 | Review API containerization | Verify all APIs are containerized | 2 | Low | Low | High | APIs containerized | DevOps | API inventory | All APIs in containers
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2.2 | Implement GitVersion for APIs | Add GitVersion to API build pipelines | 3 | Medium | Low | High | 1.2.1 | DevOps | GitVersion configured | Versions calculate correctly
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2.3 | Tag API images with version+SHA | Format: myapi:v1.2.3-abc123 | 2 | Low | Low | Critical | 1.2.2, 1.1.4 | DevOps | Images tagged correctly | Tags visible in ACR
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2.4 | Test API BODE deployment | Deploy same API artifact to DEV→QA→PROD | 3 | Medium | Medium | Critical | 1.2.3 | DevOps | BODE verified for APIs | Same SHA in all envs
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | 1.2.5 | Document API BODE process | Document how APIs achieve BODE | 2 | Low | Low | Medium | 1.2.4 | DevOps | API BODE doc | Process documented
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.1 | Audit Web app configurations | Identify all environment-specific configs | 4 | Medium | Low | High | None | Frontend Dev, DevOps | Config inventory | All configs listed
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.2 | Separate .env from build artifacts | Move env vars out of build, into deployment | 6 | Medium | Medium | Critical | 1.3.1 | Frontend Dev | Config externalized | Build has no env-specific code
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.3 | Create config replacement script | Script to inject env vars at deploy time | 4 | Medium | Low | High | 1.3.2 | DevOps, Frontend Dev | Replacement script | Script tested
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.4 | Update Web build pipeline | Build once, no environment dependencies | 4 | Medium | Medium | Critical | 1.3.2 | DevOps | Pipeline updated | Single build works all envs
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.5 | Test Web BODE deployment | Deploy same artifact to DEV→QA→PROD | 4 | Medium | Medium | Critical | 1.3.3, 1.3.4 | DevOps, Frontend Dev | BODE verified for Web | Same build in all envs
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | 1.3.6 | Document Web BODE process | Document config injection at deploy time | 3 | Low | Low | Medium | 1.3.5 | DevOps | Web BODE doc | Process documented
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.1 | Audit Mobile app configurations | Identify all environment-specific configs | 4 | Medium | Low | High | None | Mobile Dev, DevOps | Config inventory | All configs listed
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.2 | Separate config from build | Move env vars out of build artifacts | 6 | High | Medium | Critical | 1.4.1 | Mobile Dev | Config externalized | Build env-agnostic
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.3 | Implement runtime config loading | App loads config at runtime from API/file | 8 | High | Medium | Critical | 1.4.2 | Mobile Dev | Runtime config works | App adapts to env
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.4 | Update Mobile build pipeline | Build once for all environments | 4 | Medium | Medium | Critical | 1.4.3 | DevOps, Mobile Dev | Pipeline updated | Single build artifact
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.5 | Test Mobile BODE deployment | Deploy same build to DEV→QA→PROD | 6 | High | High | Critical | 1.4.3, 1.4.4 | DevOps, Mobile Dev, QA | BODE verified for Mobile | Same build all envs
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | 1.4.6 | Document Mobile BODE process | Document runtime config approach | 3 | Low | Low | Medium | 1.4.5 | Mobile Dev | Mobile BODE doc | Process documented
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.1 | Audit current test coverage | Measure baseline coverage for all projects | 3 | Low | Low | High | None | QA Lead, Developers | Coverage baseline report | Current state documented
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.2 | Install Coverlet in test projects | Add Coverlet NuGet to all test projects | 2 | Low | Low | High | 1.5.1 | Developer | Coverlet installed | Test projects build
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.3 | Create coverlet.runsettings | Configure coverage settings and exclusions | 2 | Low | Low | Medium | 1.5.2 | Developer | runsettings file | Coverage collects
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.4 | Update Azure Pipelines for coverage | Add PublishCodeCoverageResults task | 2 | Low | Low | High | 1.5.3 | DevOps | Coverage in pipeline | Coverage publishes
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.5 | Create coverage dashboard | Setup Azure DevOps coverage dashboards | 2 | Low | Low | Medium | 1.5.4 | DevOps | Dashboard active | Dashboard shows data
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.6 | Set 70% coverage threshold | Configure BuildQualityChecks task | 2 | Low | Low | High | 1.5.4 | DevOps | Threshold enforced | Build fails at <70%
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.7 | Increase test coverage (if needed) | Write tests to reach 70% threshold | 20 | Medium | Low | High | 1.5.6 | All Developers | 70% coverage achieved | All projects >70%
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.8 | Configure branch policies | Require 70% coverage for PR approval | 1 | Low | Low | High | 1.5.7 | DevOps admin | Branch policy set | PR blocks on low coverage
Phase 1: Quality Gates | 1.5 Code Coverage Gates | 1.5.9 | Test coverage enforcement | Create test PR with low coverage | 1 | Low | Low | High | 1.5.8 | DevOps | Enforcement tested | PR correctly blocked
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.1 | Configure EditorConfig | Create .editorconfig for C# standards | 2 | Low | Low | Medium | None | Senior Dev | .editorconfig file | IDE respects config
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.2 | Add StyleCop Analyzers | Add StyleCop.Analyzers NuGet to projects | 3 | Low | Low | High | None | Senior Dev | StyleCop installed | Warnings appear
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.3 | Create custom ruleset | Define team-specific linting rules | 4 | Medium | Low | Medium | 1.6.2 | Senior Dev, Tech Lead | Ruleset file | Team consensus
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.4 | Fix existing violations | Clean up codebase to pass linting | 24 | Medium | Low | High | 1.6.3 | All Developers | Code passes linting | No warnings in build
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.5 | Add linting to Azure Pipelines | TreatWarningsAsErrors in build | 1 | Low | Low | High | 1.6.4 | DevOps | Linting in pipeline | Build fails on warnings
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.6 | Setup frontend linting (if applicable) | ESLint/Prettier for Web apps | 4 | Low | Low | Medium | None | Frontend Dev | Frontend linting | Frontend builds clean
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.7 | Configure pre-commit hooks | Git hooks for local linting | 2 | Low | Low | Low | 1.6.5 | Senior Dev | Pre-commit hooks | Hooks prevent bad commits
Phase 1: Quality Gates | 1.6 Linting Implementation | 1.6.8 | Document linting standards | Developer guide on linting rules | 2 | Low | Low | Medium | 1.6.5 | Senior Dev | Linting guide | Team trained
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.1 | Decide SonarQube vs SonarCloud | Evaluate self-hosted vs cloud | 2 | Low | Low | High | None | Tech Lead, DevOps | Decision made | Approval received
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.2 | Create SonarCloud org (if cloud) | Setup organization and link to ADO | 1 | Low | Low | High | 1.7.1 | DevOps admin | Org created | Org accessible
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.3 | Create projects in SonarCloud | One project per repository | 2 | Low | Low | High | 1.7.2 | DevOps admin | Projects created | All repos added
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.4 | Configure quality gates | Set A rating, 70% coverage, 0 blockers/criticals | 3 | Low | Low | High | 1.7.3 | DevOps, QA Lead | Quality gates set | Gates reviewed
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.5 | Create project-specific profiles | Customize rules per project type (API/Web/Mobile) | 4 | Medium | Low | Medium | 1.7.4 | Senior Dev, QA Lead | Profiles configured | Rules approved
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.6 | Add SonarCloud to pipelines | Add Prepare, Analyze, Publish tasks | 3 | Low | Low | High | 1.7.5 | DevOps | SonarCloud in pipeline | Analysis runs
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.7 | Make SonarCloud mandatory | Set allow_failure=false | 1 | Low | Low | High | 1.7.6 | DevOps | SonarCloud enforced | Build fails on QG fail
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.8 | Configure branch policies | Require SonarCloud pass for PRs | 1 | Low | Low | High | 1.7.7 | DevOps admin | Branch policy set | PR blocked on fail
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.9 | Test quality gate enforcement | Create PR that fails quality gate | 2 | Low | Low | High | 1.7.8 | DevOps | Enforcement tested | PR correctly blocked
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | 1.7.10 | Setup SonarCloud dashboard | Create dashboard for leadership | 2 | Low | Low | Low | 1.7.6 | DevOps | Dashboard created | Metrics visible
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.1 | Select SAST tool | Evaluate Checkmarx, Fortify, Veracode, or Azure | 3 | Medium | Low | High | None | Security, DevOps | Tool selected | Budget approved
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.2 | Setup SAST tool account | Configure account and integration | 2 | Low | Low | High | 1.8.1 | Security, DevOps | Account setup | Can access portal
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.3 | Configure SAST scan in pipeline | Add SAST task to Azure Pipelines | 3 | Medium | Low | High | 1.8.2 | DevOps, Security | SAST in pipeline | Scan executes
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.4 | Define vulnerability thresholds | Block on Critical, fail on High (>5) | 3 | Medium | Medium | High | 1.8.3 | Security, Tech Lead | Thresholds set | Policy documented
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.5 | Run baseline scan | Scan all projects, document current state | 4 | Low | Low | High | 1.8.3 | Security | Baseline report | Known issues documented
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.6 | Remediate critical vulnerabilities | Fix all critical and high issues | 20 | High | Medium | Critical | 1.8.5 | Developers, Security | Criticals fixed | Clean scan achieved
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.7 | Make SAST scan mandatory | Enforce thresholds in pipeline | 1 | Low | Low | High | 1.8.6 | DevOps | SAST enforced | Build fails on threshold
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.8 | Configure Dependabot/Renovate | Automated dependency updates | 2 | Low | Low | Medium | None | DevOps | Dep updates automated | PRs auto-created
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.9 | Setup security scanning dashboard | Centralized security metrics view | 2 | Low | Low | Medium | 1.8.7 | Security, DevOps | Dashboard created | Metrics tracked
Phase 1: Quality Gates | 1.8 SAST Scanning | 1.8.10 | Create security incident runbook | Process for handling security alerts | 3 | Low | Low | High | 1.8.7 | Security | Runbook document | Team trained
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.1 | Create CODEOWNERS file | Define ownership for critical code areas | 3 | Low | Low | High | None | Tech Lead | CODEOWNERS file | Test PR routing
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.2 | Configure main branch protection | Require 2 reviewers, all checks, linked work item, no force push | 2 | Low | Low | Critical | 1.5.8, 1.7.8, 1.8.7 | DevOps admin | Main protected | Test PR to main
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.3 | Configure develop branch protection | Require 1 reviewer, all checks, no force push | 2 | Low | Low | High | 1.5.8, 1.7.8, 1.8.7 | DevOps admin | Develop protected | Test PR to develop
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.4 | Configure release/* protection | Require 1-2 reviewers, all checks | 1 | Low | Low | High | 1.5.8, 1.7.8, 1.8.7 | DevOps admin | Release/* protected | Test PR to release
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.5 | Configure hotfix/* protection | Require 1 senior reviewer, all checks | 1 | Low | Low | High | 1.5.8, 1.7.8, 1.8.7 | DevOps admin | Hotfix/* protected | Test PR to hotfix
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.6 | Configure feature/* policies | Require 1 reviewer, all checks | 1 | Low | Low | Medium | 1.5.8, 1.7.8, 1.8.7 | DevOps admin | Feature/* protected | Test PR to feature
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.7 | Configure auto-complete settings | Allow auto-complete after approvals | 1 | Low | Low | Low | 1.9.2-1.9.6 | DevOps admin | Auto-complete configured | Test auto-merge
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.8 | Document PR review process | Guidelines for code reviewers | 3 | Low | Low | High | 1.9.1-1.9.6 | Tech Lead | Review guidelines | Team training
Phase 1: Quality Gates | 1.9 Branch Protection Policies | 1.9.9 | Test all branch protections | Verify policies enforce correctly | 2 | Low | Low | Critical | 1.9.1-1.9.7 | DevOps | All policies tested | All blocks work
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.1 | Document current branch structure | Map all existing branches and purposes | 3 | Low | Low | High | Phase 1 complete | Tech Lead | Current structure doc | All branches documented
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.2 | Analyze dev-6.0.0 commits | Git log, open PRs, pending work | 3 | Medium | Low | High | 2.1.1 | Tech Lead | Dev analysis doc | All commits catalogued
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.3 | Analyze intg commits | Identify unique commits vs dev | 3 | Medium | Low | High | 2.1.2 | Tech Lead | Intg analysis doc | Unique commits listed
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.4 | Analyze qa commits | Identify unique commits vs intg | 3 | Medium | Low | High | 2.1.3 | Tech Lead | QA analysis doc | Unique commits listed
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.5 | Analyze stage commits | Identify unique commits vs qa | 3 | Medium | Low | High | 2.1.4 | Tech Lead | Stage analysis doc | Unique commits listed
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.6 | Analyze main (prod) state | Document production code state | 2 | Low | Low | Critical | 2.1.5 | Tech Lead | Main state doc | Prod code verified
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.7 | Create GitFlow mapping plan | Map current → develop/release/main | 4 | Medium | Medium | Critical | 2.1.2-2.1.6 | Tech Lead, Senior Dev | Migration plan doc | Architecture review
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.8 | Identify work to preserve | List all commits that must migrate | 3 | Medium | Low | High | 2.1.7 | Tech Lead | Preservation checklist | No work will be lost
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.9 | Create rollback plan | Document rollback if migration fails | 3 | Low | Low | Critical | 2.1.7 | Tech Lead, DevOps | Rollback plan | Plan reviewed
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | 2.1.10 | Get migration approval | Present plan to leadership | 2 | Low | Low | Critical | 2.1.7-2.1.9 | Tech Lead | Approval received | Green light to proceed
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.1 | Announce code freeze | Notify team of migration window | 1 | Low | Low | High | 2.1.10 | Tech Lead | Announcement sent | Team acknowledged
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.2 | Create backup tags | Tag all branches: backup-{branch}-{date} | 1 | Low | Low | Critical | 2.2.1 | Tech Lead | Backup tags created | All tags verified
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.3 | Export current branch state | Git log --all --oneline --graph > pre-migration.txt | 1 | Low | Low | Critical | 2.2.2 | Tech Lead | State exported | File saved
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.4 | Create develop branch | git checkout -b develop from main | 1 | Low | Low | Critical | 2.2.3 | Tech Lead | Develop created | Branch visible
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.5 | Merge dev-6.0.0 to develop | Merge all dev work to new develop | 3 | Medium | Medium | Critical | 2.2.4, 2.1.8 | Tech Lead | Dev work in develop | All commits present
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.6 | Cherry-pick unique intg commits | Apply unique intg commits to develop | 2 | Medium | Medium | High | 2.2.5, 2.1.3 | Tech Lead | Intg work preserved | No conflicts
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.7 | Cherry-pick unique qa commits | Apply unique qa commits to develop | 2 | Medium | Medium | High | 2.2.6, 2.1.4 | Tech Lead | QA work preserved | No conflicts
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.8 | Cherry-pick unique stage commits | Apply unique stage commits to develop | 2 | Medium | Medium | High | 2.2.7, 2.1.5 | Tech Lead | Stage work preserved | No conflicts
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.9 | Verify all work preserved | Compare new vs old, ensure nothing lost | 3 | High | Medium | Critical | 2.2.8 | Tech Lead, Senior Dev | Verification passed | All commits accounted
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.10 | Create initial release branch (if needed) | release/v6.1.0 from develop | 1 | Low | Low | Medium | 2.2.9 | Release Manager | Release branch created | Branch ready for QA
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.11 | Set develop as default branch | Change Azure DevOps default branch | 1 | Low | Low | High | 2.2.9 | DevOps admin | Default changed | Develop is default
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.12 | Push all new branches | Push develop, release/* to remote | 1 | Low | Low | Critical | 2.2.11 | Tech Lead | Branches pushed | Visible in ADO
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.13 | Apply branch protection policies | Enable policies on new branches | 1 | Low | Low | Critical | 2.2.12, 1.9 complete | DevOps admin | Policies applied | Protections active
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | 2.2.14 | Test new branch structure | Create test feature branch and PR | 2 | Low | Low | Critical | 2.2.13 | Developer | Test successful | GitFlow works
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.1 | Create GitFlow overview document | High-level GitFlow explanation | 3 | Low | Low | High | 2.2.14 | Tech Lead | Overview doc | Clear and concise
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.2 | Document feature branch workflow | How to create and merge features | 3 | Low | Low | High | 2.3.1 | Tech Lead | Feature workflow doc | Step-by-step guide
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.3 | Document bugfix workflow | How to create and merge bugfixes | 2 | Low | Low | High | 2.3.1 | Tech Lead | Bugfix workflow doc | Clear examples
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.4 | Document release workflow | How release branches work | 3 | Low | Low | High | 2.3.1 | Tech Lead, Release Mgr | Release workflow doc | Process clear
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.5 | Document hotfix workflow | Emergency hotfix process | 3 | Low | Low | Critical | 2.3.1 | Tech Lead | Hotfix workflow doc | Emergency process clear
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.6 | Create Git command cheat sheet | Quick reference for common operations | 2 | Low | Low | Medium | 2.3.1-2.3.5 | Tech Lead | Cheat sheet | Easy to follow
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.7 | Create visual flow diagrams | Diagram showing all GitFlow branches | 3 | Low | Low | Medium | 2.3.1 | Tech Lead | Flow diagrams | Visually clear
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.8 | Document branch naming conventions | feature/*, bugfix/*, hotfix/*, release/* | 2 | Low | Low | High | 2.3.1 | Tech Lead | Naming conventions doc | Standards clear
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.9 | Create commit message guidelines | Conventional commits format | 2 | Low | Low | Medium | None | Tech Lead | Commit guidelines | Format defined
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.10 | Create FAQ document | Common questions and answers | 3 | Low | Low | Medium | 2.3.1-2.3.9 | Tech Lead | FAQ doc | Covers common issues
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.11 | Setup Git hooks for branch naming | Pre-push hooks to enforce naming | 3 | Medium | Low | Low | 2.3.8 | Senior Dev | Git hooks ready | Hooks work locally
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.12 | Create troubleshooting guide | Common problems and solutions | 2 | Low | Low | Medium | 2.3.1-2.3.9 | Tech Lead | Troubleshooting doc | Solutions provided
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | 2.3.13 | Update Confluence/Wiki | Update all documentation links | 2 | Low | Low | Medium | 2.3.1-2.3.12 | Tech Lead | Wiki updated | All links work
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.1 | Rename dev-6.0.0 to deprecated/ | Archive old dev branch | 1 | Low | Low | High | 2.2.14 | DevOps | Branch renamed | No longer default
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.2 | Rename intg to deprecated/ | Archive old intg branch | 1 | Low | Low | High | 2.4.1 | DevOps | Branch renamed | Archived
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.3 | Rename qa to deprecated/ | Archive old qa branch | 1 | Low | Low | High | 2.4.2 | DevOps | Branch renamed | Archived
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.4 | Rename stage to deprecated/ | Archive old stage branch | 1 | Low | Low | High | 2.4.3 | DevOps | Branch renamed | Archived
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.5 | Update pipeline triggers | Remove triggers for deprecated branches | 2 | Low | Low | High | 2.4.1-2.4.4 | DevOps | Pipelines updated | No old branch triggers
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.6 | Communicate branch deprecation | Notify team of old branch status | 1 | Low | Low | Medium | 2.4.5 | Tech Lead | Communication sent | Team aware
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.7 | Monitor for old branch usage | Watch for attempts to use old branches (2 weeks) | 5 | Low | Low | Medium | 2.4.6 | DevOps | No usage detected | Ready to delete
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.8 | Delete remote deprecated branches | Remove deprecated branches from remote | 1 | Low | Low | Low | 2.4.7 | DevOps | Branches deleted | Confirmed deleted
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | 2.4.9 | Document decommissioning | Record what was decommissioned and when | 1 | Low | Low | Low | 2.4.8 | DevOps | Decommission doc | History preserved
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.1 | Design build pipeline architecture | Single build, artifact promotion model | 4 | Medium | Low | Critical | Phase 2 complete | DevOps, Tech Lead | Architecture doc | Design reviewed
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.2 | Create build-pipeline.yml | Main build pipeline YAML | 4 | Medium | Low | Critical | 3.1.1 | DevOps | Build YAML created | Syntax valid
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.3 | Add trigger configuration | Triggers for main, develop, release/*, hotfix/* | 2 | Low | Low | High | 3.1.2 | DevOps | Triggers configured | Branches trigger correctly
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.4 | Add GitVersion stage | Calculate semantic version | 2 | Low | Low | High | 3.1.2, 1.2.2 | DevOps | GitVersion in YAML | Versions calculate
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.5 | Add build stage | dotnet build for all projects | 2 | Low | Low | Critical | 3.1.2 | DevOps | Build stage added | Projects build
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.6 | Add unit test stage | Run unit tests with coverage | 2 | Low | Low | Critical | 3.1.5, 1.5 complete | DevOps | Unit test stage | Tests run
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.7 | Add integration test stage | Run integration tests | 2 | Low | Low | High | 3.1.5 | DevOps | Integration test stage | Tests execute
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.8 | Add linting stage | StyleCop/ESLint checks | 1 | Low | Low | High | 3.1.5, 1.6 complete | DevOps | Linting stage | Linting runs
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.9 | Add SonarCloud stages | Prepare, Analyze, Publish | 2 | Low | Low | High | 3.1.5, 1.7 complete | DevOps | SonarCloud stages | Analysis runs
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.10 | Add SAST scan stage | Security scanning | 2 | Low | Low | High | 3.1.5, 1.8 complete | DevOps | SAST stage | Scan executes
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.11 | Add Docker build stage | Build container images | 3 | Medium | Low | Critical | 3.1.5 | DevOps | Docker build stage | Images build
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.12 | Add Docker tag & push stage | Tag with version+SHA, push to ACR | 2 | Low | Low | Critical | 3.1.11, 1.2.3 | DevOps | Docker push stage | Images in ACR
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.13 | Add .dacpac build stage | Build SQL projects | 2 | Low | Low | Critical | 3.1.2 | DevOps | .dacpac build stage | .dacpac created
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.14 | Add .dacpac publish stage | Publish to Artifact Feed | 2 | Low | Low | Critical | 3.1.13 | DevOps | .dacpac publish stage | Artifacts in feed
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | 3.1.15 | Test build pipeline end-to-end | Full pipeline test | 4 | Medium | Medium | Critical | 3.1.2-3.1.14 | DevOps | Build pipeline works | All artifacts created
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.1 | Design deployment architecture | Parameterized deploy with artifact selection | 4 | Medium | Low | Critical | 3.1.15 | DevOps, Tech Lead | Deploy architecture doc | Design approved
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.2 | Create deploy-pipeline.yml | Main deployment pipeline YAML | 4 | Medium | Medium | Critical | 3.2.1 | DevOps | Deploy YAML created | Syntax valid
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.3 | Add environment parameters | Parameters for DEV/QA/STG/PROD | 2 | Low | Low | High | 3.2.2 | DevOps | Parameters added | Env selectable
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.4 | Add artifact version parameter | Parameter to select artifact version/tag | 3 | Medium | Low | Critical | 3.2.2 | DevOps | Version selection works | Can pick any version
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.5 | Add Docker image download stage | Pull image from ACR by tag | 2 | Low | Low | Critical | 3.2.4, 1.1.5 | DevOps | Image download works | Correct image pulled
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.6 | Add .dacpac download stage | Download .dacpac from Artifact Feed | 2 | Low | Low | Critical | 3.2.4, 1.1.6 | DevOps | .dacpac download works | Correct version retrieved
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.7 | Add database backup stage | Backup DB before deployment | 3 | Medium | Low | Critical | 3.2.6 | DevOps, DB Dev | Backup stage added | Backup executes
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.8 | Add .dacpac deployment stage | Deploy database changes | 3 | Medium | Medium | Critical | 3.2.7 | DevOps, DB Dev | .dacpac deploy stage | Schema updates
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.9 | Add application deployment stage | Deploy to K8s/App Service | 4 | Medium | Medium | Critical | 3.2.5 | DevOps | App deploy stage | App deploys
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.10 | Add config replacement stage | Inject environment-specific config | 3 | Medium | Low | High | 3.2.9, 1.3.3 | DevOps | Config injection works | Correct config applied
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.11 | Add health check stage | Verify deployment health | 3 | Medium | Low | Critical | 3.2.9 | DevOps | Health check stage | Health verified
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.12 | Add smoke test stage | Run critical endpoint tests | 3 | Medium | Low | High | 3.2.11 | DevOps, QA | Smoke test stage | Tests pass
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.13 | Add approval gates | Manual approval for QA/STG/PROD | 2 | Low | Low | High | 3.2.2 | DevOps admin | Approvals configured | Gate workflow tested
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.14 | Add rollback on failure | Auto-rollback if health fails | 4 | High | Medium | High | 3.2.11 | DevOps | Rollback logic added | Rollback tested
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.15 | Add deployment notifications | Teams/Slack/Email notifications | 2 | Low | Low | Low | 3.2.2 | DevOps | Notifications work | Messages sent
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.16 | Test deploy pipeline to DEV | Full deployment to DEV | 4 | Medium | Medium | Critical | 3.2.2-3.2.15 | DevOps | DEV deploy successful | App running
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.17 | Test deploy pipeline to QA | Full deployment to QA | 3 | Medium | Medium | Critical | 3.2.16 | DevOps | QA deploy successful | App running
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.18 | Test deploy pipeline to STG | Full deployment to STG | 3 | Medium | Medium | High | 3.2.17 | DevOps | STG deploy successful | App running
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | 3.2.19 | Test deploy pipeline to PROD | Full deployment to PROD (test) | 4 | High | High | Critical | 3.2.18 | DevOps, Tech Lead | PROD deploy successful | App running
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.1 | Create service principals for pipelines | SP for ACR, Artifact Feed, K8s access | 3 | Medium | Medium | Critical | None | DevOps, Security | SPs created | Access works
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.2 | Configure Key Vault integration | Store secrets in Azure Key Vault | 3 | Medium | Low | High | 3.3.1 | DevOps, Security | Key Vault configured | Secrets retrieved
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.3 | Setup RBAC for environments | Least privilege access per environment | 3 | Medium | Medium | High | 3.3.1 | DevOps, Security | RBAC configured | Access verified
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.4 | Configure pipeline permissions | Permissions for artifact access | 2 | Low | Low | High | 3.3.1 | DevOps admin | Permissions set | Pipelines can access
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.5 | Test security configuration | Verify no unauthorized access possible | 2 | Medium | Low | High | 3.3.1-3.3.4 | Security, DevOps | Security tested | All access controlled
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | 3.3.6 | Document security setup | Document service principals and access | 2 | Low | Low | High | 3.3.5 | Security | Security doc | Setup documented
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.1 | Document build pipeline | How build pipeline works | 3 | Low | Low | High | 3.1.15 | DevOps | Build pipeline doc | Clear documentation
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.2 | Document deployment pipeline | How to deploy to each environment | 4 | Low | Low | High | 3.2.19 | DevOps | Deploy pipeline doc | Step-by-step guide
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.3 | Document artifact selection | How to choose artifact version | 2 | Low | Low | High | 3.2.4 | DevOps | Artifact selection doc | Process clear
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.4 | Create pipeline troubleshooting guide | Common issues and solutions | 3 | Low | Low | Medium | 3.1.15, 3.2.19 | DevOps | Troubleshooting guide | Solutions provided
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.5 | Create pipeline architecture diagrams | Visual representation of pipelines | 3 | Low | Low | Medium | 3.1.1, 3.2.1 | DevOps | Architecture diagrams | Clear visuals
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | 3.4.6 | Document environment variables | All env vars and their purposes | 2 | Low | Low | High | 3.2.10 | DevOps | Env var documentation | All vars documented
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.1 | Verify .dacpac artifact feed exists | Check if feed is already setup | 1 | Low | Low | High | 1.1.3 | DevOps | Status verified | Feed exists or not
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.2 | Create .dacpac artifact feed (if needed) | Setup NuGet feed for .dacpac | 2 | Low | Low | High | 4.1.1 | DevOps | Feed created | Feed accessible
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.3 | Configure .dacpac versioning | Version .dacpac with GitVersion | 2 | Low | Low | High | 3.1.4, 4.1.1 | DevOps, DB Dev | Versioning works | .dacpac has version
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.4 | Test .dacpac publish | Publish .dacpac to feed | 2 | Low | Low | High | 4.1.3 | DevOps | Publish tested | .dacpac in feed
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.5 | Test .dacpac download | Download specific version from feed | 2 | Low | Low | High | 4.1.4 | DevOps | Download tested | Correct version retrieved
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | 4.1.6 | Document .dacpac artifact strategy | How .dacpac artifacts are managed | 2 | Low | Low | Medium | 4.1.3-4.1.5 | DevOps, DB Dev | .dacpac strategy doc | Process documented
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.1 | Verify Azure Storage exists | Check backup storage account | 1 | Low | Low | High | None | DevOps | Storage verified | Exists or not
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.2 | Create backup storage (if needed) | Create storage account and container | 2 | Low | Low | High | 4.2.1 | DevOps | Storage created | Can write to storage
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.3 | Create backup script | PowerShell/Bash to backup database | 3 | Medium | Low | Critical | 4.2.2 | DB Developer | Backup script | Script tested
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.4 | Integrate backup into deploy pipeline | Add backup before .dacpac deploy | 2 | Low | Low | Critical | 4.2.3, 3.2.7 | DevOps | Backup in pipeline | Backup runs
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.5 | Configure backup retention | 7/30/60/90 day retention by env | 2 | Low | Low | High | 4.2.2 | DevOps | Retention configured | Old backups delete
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.6 | Create restore script | PowerShell/Bash to restore from backup | 3 | Medium | Medium | Critical | 4.2.3 | DB Developer | Restore script | Script tested
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.7 | Test backup in DEV | Run backup, verify file created | 2 | Low | Low | High | 4.2.4 | DevOps, DB Dev | Backup tested | Backup file exists
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.8 | Test restore in DEV | Restore from backup, verify data | 3 | Medium | Low | Critical | 4.2.6, 4.2.7 | DB Developer | Restore tested | Data intact
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.9 | Document backup/restore process | Complete backup/restore runbook | 3 | Low | Low | Critical | 4.2.3-4.2.8 | DB Developer | Backup runbook | Process documented
Phase 4: Database Strategy | 4.2 Database Backup & Restore | 4.2.10 | Train team on backup/restore | Training session on procedures | 2 | Low | Low | High | 4.2.9 | DB Developer | Team trained | Team confident
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.1 | Create rollback decision tree | Flowchart for rollback scenarios | 3 | Low | Low | High | None | DB Developer, Tech Lead | Decision tree | Clear guidance
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.2 | Test app-only rollback | Rollback app without DB change | 2 | Low | Low | Critical | 3.2.14 | DevOps, DB Dev | App rollback tested | Works without DB change
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.3 | Test app + additive schema rollback | Rollback with backward-compatible schema | 3 | Medium | Low | Critical | 4.2.8 | DB Developer | Additive rollback tested | Works without DB restore
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.4 | Test breaking schema scenario | Attempt rollback with breaking schema | 3 | Medium | Medium | High | 4.2.8 | DB Developer | Breaking scenario tested | Requires DB restore
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.5 | Measure rollback times | Time app vs DB restore rollbacks | 2 | Low | Low | High | 4.3.2-4.3.4 | DevOps, DB Dev | Timing report | Times documented
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.6 | Create rollback runbook | Step-by-step rollback procedures | 4 | Low | Low | Critical | 4.3.1-4.3.5 | DB Developer, DevOps | Rollback runbook | Clear procedures
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.7 | Conduct rollback drill | Practice rollback with team | 3 | Low | Low | High | 4.3.6 | All team | Drill completed | Team confident
Phase 4: Database Strategy | 4.3 Rollback Testing | 4.3.8 | Document lessons learned | Capture learnings from testing | 2 | Low | Low | Medium | 4.3.1-4.3.7 | DB Developer | Lessons doc | Improvements identified
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.1 | Create test feature branch | feature/test-pipeline from develop | 1 | Low | Low | High | Phase 3, 4 complete | Developer | Branch created | Branch exists
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.2 | Implement test feature | Simple feature to test pipeline | 4 | Low | Low | High | 5.1.1 | Developer | Feature implemented | Code ready
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.3 | Create PR to develop | Open PR with test feature | 1 | Low | Low | High | 5.1.2 | Developer | PR created | PR visible
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.4 | Verify all quality gates run | Coverage, linting, SonarCloud, SAST | 2 | Low | Medium | Critical | 5.1.3 | DevOps, Developer | All gates executed | All checks pass
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.5 | Verify branch protection works | Confirm reviewers required | 1 | Low | Low | High | 5.1.4 | Developer | Protection verified | PR needs approval
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.6 | Complete PR review and merge | Approve and merge PR | 1 | Low | Low | High | 5.1.5 | Senior Dev | PR merged | Merged to develop
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.7 | Verify build triggers on merge | Build pipeline runs automatically | 1 | Low | Low | Critical | 5.1.6 | DevOps | Build triggered | Pipeline ran
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.8 | Verify artifacts created | Docker image and .dacpac created | 2 | Low | Low | Critical | 5.1.7 | DevOps | Artifacts verified | All artifacts exist
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.9 | Verify artifact versioning | Check version tags are correct | 1 | Low | Low | Critical | 5.1.8 | DevOps | Versions verified | Tags correct
Phase 5: Testing & Validation | 5.1 Development Branch Testing | 5.1.10 | Document dev branch test results | Record findings and issues | 2 | Low | Low | High | 5.1.1-5.1.9 | DevOps | Test report | Results documented
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.1 | Create test release branch | release/v6.1.0 from develop | 1 | Low | Low | High | 5.1.10 | Release Manager | Release created | Branch exists
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.2 | Update version in release | Bump version numbers | 1 | Low | Low | High | 5.2.1 | Release Manager | Version updated | Version correct
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.3 | Trigger release build | Build pipeline for release branch | 1 | Low | Low | High | 5.2.2 | Release Manager | Build triggered | Pipeline ran
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.4 | Verify release artifacts | Check artifacts have release version | 2 | Low | Low | Critical | 5.2.3 | DevOps | Artifacts verified | Release version tagged
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.5 | Deploy release to QA | Use deploy pipeline to QA | 2 | Low | Medium | High | 5.2.4 | Release Manager | Deployed to QA | App in QA
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.6 | Verify artifact selection works | Confirm correct artifact deployed | 2 | Low | Low | Critical | 5.2.5 | DevOps | Artifact verified | Correct version in QA
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.7 | Test QA approval gate | Verify approval required | 1 | Low | Low | High | 5.2.5 | Release Manager | Approval tested | Gate works
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.8 | Deploy release to STG | Deploy to staging environment | 2 | Low | Medium | High | 5.2.7 | Release Manager | Deployed to STG | App in STG
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.9 | Create PR release to main | Open PR from release to main | 1 | Low | Low | High | 5.2.8 | Release Manager | PR created | PR ready
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.10 | Merge release to main | Complete release merge | 1 | Low | Low | Critical | 5.2.9 | Tech Lead | Merged to main | Release in main
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.11 | Deploy to PROD | Deploy release to production | 3 | Medium | High | Critical | 5.2.10 | Release Manager | Deployed to PROD | App in PROD
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.12 | Verify BODE in release | Same artifact in QA, STG, PROD | 2 | Low | Low | Critical | 5.2.11 | DevOps | BODE verified | SHA matches all envs
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.13 | Merge release back to develop | Sync develop with main | 1 | Low | Low | High | 5.2.10 | Release Manager | Merged to develop | Develop updated
Phase 5: Testing & Validation | 5.2 Release Branch Testing | 5.2.14 | Document release test results | Record findings | 2 | Low | Low | High | 5.2.1-5.2.13 | Release Manager | Test report | Process validated
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.1 | Simulate production bug | Create test bug scenario | 1 | Low | Low | High | 5.2.14 | Tech Lead | Bug scenario ready | Issue defined
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.2 | Create hotfix branch | hotfix/test-fix from main | 1 | Low | Low | Critical | 5.3.1 | Developer | Hotfix created | Branch exists
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.3 | Implement hotfix | Fix the simulated bug | 2 | Low | Low | Critical | 5.3.2 | Developer | Fix implemented | Bug fixed
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.4 | Create PR to main | Fast-track PR for hotfix | 1 | Low | Low | Critical | 5.3.3 | Developer | PR created | PR labeled hotfix
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.5 | Expedited review | Quick senior dev review | 1 | Low | Low | Critical | 5.3.4 | Senior Dev | PR approved | Ready to merge
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.6 | Merge hotfix to main | Complete merge | 1 | Low | Low | Critical | 5.3.5 | Developer | Merged to main | Hotfix in main
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.7 | Verify hotfix build | Build pipeline runs for hotfix | 1 | Low | Low | Critical | 5.3.6 | DevOps | Build successful | Artifacts created
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.8 | Deploy hotfix to PROD | Emergency deployment | 2 | Medium | High | Critical | 5.3.7 | DevOps | Deployed to PROD | Fix in production
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.9 | Verify hotfix works | Confirm bug is fixed | 1 | Low | Low | Critical | 5.3.8 | QA, Developer | Fix verified | Bug resolved
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.10 | Merge hotfix to develop | Sync develop with main | 1 | Low | Low | High | 5.3.6 | Developer | Merged to develop | Develop updated
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.11 | Measure hotfix time | Total time from bug to fix | 1 | Low | Low | Critical | 5.3.1-5.3.9 | Tech Lead | Time measured | < 4 hours target
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | 5.3.12 | Document hotfix test results | Record process and timing | 2 | Low | Low | Critical | 5.3.1-5.3.11 | Tech Lead | Hotfix report | Process validated
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.1 | Measure build pipeline time | Time full build pipeline | 2 | Low | Low | High | 5.1.10 | DevOps | Build time measured | < 20 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.2 | Measure deploy to DEV time | Time DEV deployment | 1 | Low | Low | Medium | 5.1.10 | DevOps | DEV deploy time | < 5 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.3 | Measure deploy to QA time | Time QA deployment | 1 | Low | Low | Medium | 5.2.14 | DevOps | QA deploy time | < 10 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.4 | Measure deploy to PROD time | Time PROD deployment | 1 | Low | Low | High | 5.2.14 | DevOps | PROD deploy time | < 15 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.5 | Test concurrent feature builds | 3-5 feature branches building simultaneously | 3 | Medium | Low | Medium | 5.1.10 | DevOps | Concurrent test done | No bottlenecks
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.6 | Measure rollback time | Time app rollback | 2 | Low | Low | High | 4.3.2 | DevOps | Rollback time measured | < 5 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.7 | Measure DB restore time | Time database restore | 2 | Low | Low | High | 4.3.4 | DB Developer | Restore time measured | < 30 min target
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.8 | Test rapid deployments | Deploy 5 times in succession | 3 | Medium | Low | Medium | 5.2.14 | DevOps | Rapid deploy tested | No failures
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.9 | Identify bottlenecks | Analyze slow stages | 3 | Medium | Low | Medium | 5.4.1-5.4.8 | DevOps | Bottlenecks identified | Optimization list
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.10 | Optimize slow stages | Implement improvements | 8 | Medium | Low | Medium | 5.4.9 | DevOps | Optimizations complete | Improved times
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | 5.4.11 | Document performance baselines | Record baseline metrics | 2 | Low | Low | Medium | 5.4.1-5.4.10 | DevOps | Baseline doc | Metrics recorded
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5.1 | Test rollback scenario 1 | App bug, no DB change | 2 | Low | Low | Critical | 4.3.2 | DevOps | Scenario 1 tested | Rollback successful
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5.2 | Test rollback scenario 2 | App bug with additive schema | 3 | Medium | Low | Critical | 4.3.3 | DevOps, DB Dev | Scenario 2 tested | No DB restore needed
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5.3 | Test rollback scenario 3 | Breaking schema change | 3 | Medium | Medium | High | 4.3.4 | DB Developer | Scenario 3 tested | DB restore required
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5.4 | Test rollback scenario 4 | Simultaneous app + DB rollback | 4 | High | Medium | High | 4.3.8 | DevOps, DB Dev | Scenario 4 tested | Coordinated rollback
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | 5.5.5 | Document all rollback scenarios | Complete rollback matrix | 3 | Low | Low | Critical | 5.5.1-5.5.4 | Tech Lead | Rollback matrix | All scenarios documented
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.1 | Consolidate all documentation | Gather all docs created so far | 3 | Low | Low | High | Phase 5 complete | Tech Lead | Docs consolidated | All docs collected
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.2 | Create quick start guide | 5-minute quick start for developers | 3 | Low | Low | High | 6.1.1 | Tech Lead | Quick start guide | Easy to follow
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.3 | Create video tutorials | Record 3-5 minute tutorial videos | 6 | Medium | Low | Medium | 6.1.1 | Tech Lead | Tutorial videos | Videos uploaded
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.4 | Create FAQ document | Comprehensive FAQ | 3 | Low | Low | High | 6.1.1 | Tech Lead | FAQ doc | Common questions covered
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.5 | Update Confluence/Wiki | Publish all documentation | 4 | Low | Low | High | 6.1.1-6.1.4 | Tech Lead | Wiki updated | All docs accessible
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.6 | Create training slides | Presentation for training sessions | 4 | Low | Low | High | 6.1.1 | Tech Lead | Training slides | Ready to present
Phase 6: Rollout | 6.1 Documentation Preparation | 6.1.7 | Share documentation links | Send to all developers | 1 | Low | Low | High | 6.1.5 | Tech Lead | Links shared | Team has access
Phase 6: Rollout | 6.2 Team Training | 6.2.1 | Schedule training sessions | Book rooms, send invites | 2 | Low | Low | High | 6.1.7 | Tech Lead | Sessions scheduled | Calendar invites sent
Phase 6: Rollout | 6.2 Team Training | 6.2.2 | Conduct training session 1 | GitFlow overview (90 min) | 2 | Low | Low | High | 6.2.1 | Tech Lead | Session 1 complete | Team attended
Phase 6: Rollout | 6.2 Team Training | 6.2.3 | Conduct training session 2 | Pipeline deep dive (90 min) | 2 | Low | Low | High | 6.2.2 | Tech Lead, DevOps | Session 2 complete | Questions answered
Phase 6: Rollout | 6.2 Team Training | 6.2.4 | Conduct hands-on workshop | Guided practice (2 hours) | 2 | Low | Low | High | 6.2.3 | Tech Lead, Senior Dev | Workshop complete | Hands-on practice
Phase 6: Rollout | 6.2 Team Training | 6.2.5 | Office hours - Week 1 | Daily 1-hour office hours | 5 | Low | Low | High | 6.2.4 | Tech Lead | Office hours done | Questions answered
Phase 6: Rollout | 6.2 Team Training | 6.2.6 | Gather training feedback | Survey team on training | 1 | Low | Low | Medium | 6.2.2-6.2.4 | Tech Lead | Feedback collected | Improvements noted
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.1 | Select pilot team | Choose low-risk team (3-5 people) | 1 | Low | Low | High | 6.2.6 | Tech Lead | Pilot team selected | Team committed
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.2 | Pilot team kickoff | Kickoff meeting with pilot team | 1 | Low | Low | High | 6.3.1 | Tech Lead | Kickoff complete | Team ready
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.3 | Migrate pilot repositories | Move pilot repos to GitFlow | 4 | Medium | Medium | High | 6.3.2 | DevOps, Tech Lead | Repos migrated | GitFlow active
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.4 | Shadow pilot team - Day 1 | Full support first day | 8 | Low | Low | High | 6.3.3 | Tech Lead, DevOps | Day 1 support done | No blockers
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.5 | Shadow pilot team - Week 1 | Daily check-ins | 10 | Low | Low | High | 6.3.4 | Tech Lead | Week 1 complete | Team productive
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.6 | Gather pilot feedback | Detailed feedback from pilot | 2 | Low | Low | High | 6.3.5 | Tech Lead | Feedback collected | Issues identified
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.7 | Address pilot issues | Fix problems found in pilot | 8 | Medium | Low | High | 6.3.6 | Tech Lead, DevOps | Issues resolved | Process improved
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.8 | Update documentation from pilot | Incorporate pilot learnings | 3 | Low | Low | High | 6.3.7 | Tech Lead | Docs updated | Improvements included
Phase 6: Rollout | 6.3 Pilot Team Rollout | 6.3.9 | Pilot go/no-go decision | Decision to proceed with full rollout | 1 | Low | Low | Critical | 6.3.8 | Tech Lead, Management | Decision made | Approved to proceed
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.1 | Create rollout schedule | Plan team-by-team migration (1-2 teams/week) | 2 | Low | Low | High | 6.3.9 | Tech Lead | Schedule created | Teams notified
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.2 | Migrate Team A | Full migration for Team A | 6 | Medium | Medium | High | 6.4.1 | DevOps, Tech Lead | Team A migrated | Team productive
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.3 | Support Team A - Week 1 | Daily check-ins with Team A | 5 | Low | Low | High | 6.4.2 | Tech Lead | Team A support done | Team confident
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.4 | Migrate Team B | Full migration for Team B | 6 | Medium | Medium | High | 6.4.2 | DevOps, Tech Lead | Team B migrated | Team productive
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.5 | Support Team B - Week 1 | Daily check-ins with Team B | 5 | Low | Low | High | 6.4.4 | Tech Lead | Team B support done | Team confident
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.6 | Migrate Team C | Full migration for Team C | 6 | Medium | Medium | High | 6.4.4 | DevOps, Tech Lead | Team C migrated | Team productive
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.7 | Support Team C - Week 1 | Daily check-ins with Team C | 5 | Low | Low | High | 6.4.6 | Tech Lead | Team C support done | Team confident
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.8 | Migrate remaining teams | Migrate all other teams | 12 | Medium | Medium | High | 6.4.6 | DevOps, Tech Lead | All teams migrated | Everyone on GitFlow
Phase 6: Rollout | 6.4 Full Team Rollout | 6.4.9 | Extended support period | 2 weeks ongoing support for all | 10 | Low | Low | High | 6.4.8 | Tech Lead, DevOps | Support period complete | Teams stable
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.1 | Verify all teams migrated | Confirm no team on old process | 2 | Low | Low | Critical | 6.4.9 | Tech Lead | All teams confirmed | 100% migration
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.2 | Archive old pipeline definitions | Export old pipeline YAML for history | 2 | Low | Low | Medium | 6.5.1 | DevOps | Pipelines archived | History preserved
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.3 | Disable old pipelines | Disable/delete old pipelines | 2 | Low | Low | High | 6.5.2 | DevOps | Old pipelines disabled | Can't trigger
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.4 | Final branch cleanup | Delete all deprecated/* branches | 1 | Low | Low | Low | 6.5.1 | DevOps | Branches deleted | Cleanup complete
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.5 | Archive old documentation | Move old docs to archive folder | 2 | Low | Low | Low | 6.5.1 | Tech Lead | Docs archived | Old docs preserved
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.6 | Update all wiki links | Remove references to old process | 3 | Low | Low | Medium | 6.5.5 | Tech Lead | Links updated | No broken links
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.7 | Announce completion | Company-wide success announcement | 1 | Low | Low | Medium | 6.5.1-6.5.6 | Tech Lead | Announcement sent | Success celebrated
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.8 | Measure before/after metrics | Compare old vs new metrics | 4 | Low | Low | High | 6.5.1 | Tech Lead | Metrics report | Improvement shown
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.9 | Conduct retrospective | Team retrospective on migration | 3 | Low | Low | High | 6.5.8 | Tech Lead | Retro complete | Lessons documented
Phase 6: Rollout | 6.5 Old Process Decommissioning | 6.5.10 | Create case study | Document migration for reference | 4 | Low | Low | Low | 6.5.9 | Tech Lead | Case study | Knowledge preserved
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.1 | Evaluate LaunchDarkly | Trial LaunchDarkly, test features | 4 | Medium | Low | High | None | Tech Lead, Senior Dev | Evaluation report | Feature assessment
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.2 | Evaluate Split.io | Trial Split.io, test features | 4 | Medium | Low | High | None | Tech Lead, Senior Dev | Evaluation report | Feature assessment
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.3 | Compare LaunchDarkly vs Split.io | Cost, features, ease of use comparison | 3 | Low | Low | High | FF.1.1, FF.1.2 | Tech Lead | Comparison doc | Clear recommendation
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.4 | Get budget approval | Secure budget for selected tool | 2 | Low | Low | Critical | FF.1.3 | Tech Lead, Management | Budget approved | Funding secured
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.5 | Create tool account | Setup LaunchDarkly or Split.io account | 2 | Low | Low | High | FF.1.4 | Tech Lead, DevOps | Account created | Can access portal
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.6 | Create projects in tool | Setup projects for each application | 2 | Low | Low | High | FF.1.5 | DevOps | Projects created | All apps added
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.7 | Configure environments | Setup DEV, QA, STG, PROD environments | 2 | Low | Low | High | FF.1.6 | DevOps | Environments configured | All envs ready
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.8 | Setup SDK keys | Generate and store SDK keys securely | 2 | Low | Low | High | FF.1.7 | DevOps, Security | SDK keys generated | Keys in Key Vault
Special: Feature Flags | FF.1 Tool Selection & Setup | FF.1.9 | Configure access controls | Setup user roles and permissions | 2 | Low | Low | High | FF.1.5 | DevOps, Security | Access controls set | Permissions configured
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.1 | Design adapter architecture | Interface for provider abstraction | 4 | Medium | Low | High | FF.1.5 | Senior Dev, Tech Lead | Architecture doc | Design reviewed
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.2 | Create IFeatureFlagProvider interface | Abstract interface for feature flags | 3 | Low | Low | High | FF.2.1 | Senior Dev | Interface created | Interface defined
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.3 | Implement LaunchDarkly adapter | LaunchDarklyFeatureFlagProvider class | 8 | Medium | Low | High | FF.2.2, FF.1.8 | Senior Dev | LD adapter complete | Adapter works
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.4 | Implement Split.io adapter (optional) | SplitIoFeatureFlagProvider class | 8 | Medium | Low | Low | FF.2.2 | Senior Dev | Split adapter complete | Adapter works
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.5 | Implement InMemory adapter | InMemoryFeatureFlagProvider for testing | 4 | Low | Low | Medium | FF.2.2 | Senior Dev | InMemory adapter complete | Local testing works
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.6 | Create FeatureFlagContext class | Context for user/org targeting | 2 | Low | Low | High | FF.2.2 | Senior Dev | Context class created | Targeting works
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.7 | Implement DI configuration | Startup configuration for adapter selection | 3 | Low | Low | High | FF.2.3-FF.2.5 | Senior Dev | DI configured | Provider swappable
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.8 | Create helper extensions | Extension methods for common patterns | 4 | Low | Low | Medium | FF.2.7 | Senior Dev | Extensions created | Easy to use
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.9 | Write unit tests for adapter | Test all adapter implementations | 6 | Medium | Low | High | FF.2.3-FF.2.8 | Senior Dev | Tests written | >80% coverage
Special: Feature Flags | FF.2 C# Adapter Development | FF.2.10 | Document adapter usage | Developer guide on using adapter | 4 | Low | Low | High | FF.2.9 | Senior Dev | Adapter guide | Clear examples
Special: Feature Flags | FF.3 Integration & Testing | FF.3.1 | Add adapter to API projects | Integrate into API projects | 4 | Low | Low | High | FF.2.10 | Developers | APIs integrated | APIs use adapter
Special: Feature Flags | FF.3 Integration & Testing | FF.3.2 | Add adapter to Web projects | Integrate into Web applications | 4 | Medium | Low | High | FF.2.10 | Frontend Devs | Web integrated | Web uses adapter
Special: Feature Flags | FF.3 Integration & Testing | FF.3.3 | Add adapter to Mobile projects (if applicable) | Integrate into mobile apps | 6 | Medium | Medium | Medium | FF.2.10 | Mobile Devs | Mobile integrated | Mobile uses adapter
Special: Feature Flags | FF.3 Integration & Testing | FF.3.4 | Create test feature flags | Create flags for testing | 2 | Low | Low | High | FF.3.1-FF.3.3 | DevOps | Test flags created | Flags visible in portal
Special: Feature Flags | FF.3 Integration & Testing | FF.3.5 | Test flag evaluation | Verify flags evaluate correctly | 3 | Low | Low | High | FF.3.4 | Developers | Evaluation tested | Flags work correctly
Special: Feature Flags | FF.3 Integration & Testing | FF.3.6 | Test flag targeting | Test user/org/role targeting | 3 | Medium | Low | High | FF.3.5 | Developers | Targeting tested | Targeting works
Special: Feature Flags | FF.3 Integration & Testing | FF.3.7 | Test flag in all environments | Verify flags work in DEV/QA/STG/PROD | 4 | Medium | Low | High | FF.3.5 | DevOps, Developers | All envs tested | Works everywhere
Special: Feature Flags | FF.3 Integration & Testing | FF.3.8 | Test adapter switching | Switch from LaunchDarkly to InMemory | 2 | Low | Low | Medium | FF.3.5 | Senior Dev | Switching tested | Adapter swappable
Special: Feature Flags | FF.3 Integration & Testing | FF.3.9 | Performance test flag evaluation | Measure flag evaluation overhead | 3 | Medium | Low | Medium | FF.3.5 | Senior Dev | Performance tested | < 5ms overhead
Special: Feature Flags | FF.4 Documentation & Training | FF.4.1 | Create feature flag overview doc | What are feature flags, why use them | 3 | Low | Low | High | FF.2.10 | Tech Lead | Overview doc | Clear explanation
Special: Feature Flags | FF.4 Documentation & Training | FF.4.2 | Create flag lifecycle guide | Create, test, rollout, cleanup process | 4 | Low | Low | High | FF.4.1 | Tech Lead | Lifecycle guide | Process documented
Special: Feature Flags | FF.4 Documentation & Training | FF.4.3 | Create flag naming conventions | Standards for flag naming | 2 | Low | Low | High | FF.4.1 | Tech Lead | Naming guide | Standards clear
Special: Feature Flags | FF.4 Documentation & Training | FF.4.4 | Create flag usage patterns doc | Common patterns and anti-patterns | 4 | Low | Low | High | FF.4.1 | Senior Dev | Patterns guide | Examples provided
Special: Feature Flags | FF.4 Documentation & Training | FF.4.5 | Create LaunchDarkly portal guide | How to use LaunchDarkly UI | 3 | Low | Low | Medium | FF.1.7 | DevOps | Portal guide | UI explained
Special: Feature Flags | FF.4 Documentation & Training | FF.4.6 | Create code examples | Real code examples of flag usage | 4 | Low | Low | High | FF.3.9 | Senior Dev | Code examples | Clear examples
Special: Feature Flags | FF.4 Documentation & Training | FF.4.7 | Create training presentation | Slides for feature flag training | 4 | Low | Low | High | FF.4.1-FF.4.6 | Tech Lead | Training slides | Ready to present
Special: Feature Flags | FF.4 Documentation & Training | FF.4.8 | Conduct feature flag training | Team training session (2 hours) | 2 | Low | Low | High | FF.4.7 | Tech Lead, Senior Dev | Training complete | Team trained
Special: Feature Flags | FF.4 Documentation & Training | FF.4.9 | Create FAQ for feature flags | Common questions answered | 3 | Low | Low | Medium | FF.4.8 | Tech Lead | Flag FAQ | Questions covered
Special: Feature Flags | FF.4 Documentation & Training | FF.4.10 | Publish all flag documentation | Make all docs accessible | 2 | Low | Low | High | FF.4.1-FF.4.9 | Tech Lead | Docs published | Team has access