## Summary
GitFlow Migration Summary
Phase | Total Hours | Description
Phase 1: Quality Gates |  | Artifact repo, coverage, SonarCloud, security, linting, branch protection
Phase 2: Branching Migration |  | Branch mapping, creation, developer workflow, decommissioning
Phase 3: CI/CD Transform |  | Pipeline design, build pipeline, deploy pipeline, testing
Phase 4: Database Strategy |  | .dacpac artifacts, backup strategy, schema safety, rollback testing
Phase 5: Testing |  | Feature flow, release process, hotfix process, performance testing
Phase 6: Rollout |  | Team training, pilot rollout, full rollout, decommissioning
TOTAL HOURS
TOTAL DAYS (4-5 hrs/day)
Critical Tasks |  | Tasks marked as Critical criticality
High Risk Tasks |  | Tasks with High risk level

## GitFlow Migration Tasks
Phase | Sub-Phase | Task ID | Task Name | Task Description | Hours | Complexity | Risk Level | Criticality | Prerequisites | Skills Required | Deliverable | Validation Required
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.1 | Research Azure Artifacts options | Research Azure Artifacts Feed vs Container Registry capabilities and pricing | 2 | Low | Low | Medium | None | DevOps, Azure knowledge | Options comparison doc | Review with team
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.2 | Create Azure Container Registry | Provision ACR in Azure portal, configure authentication | 3 | Low | Low | High | 1.1.1 | Azure admin, DevOps | ACR instance configured | Test push/pull image
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.3 | Setup NuGet feed for .dacpac | Create Azure Artifacts Feed for database artifacts | 2 | Low | Low | High | 1.1.1 | Azure DevOps admin | NuGet feed configured | Test publish package
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.4 | Configure retention policies | Set retention policies: 30 days dev, 90 days releases, indefinite prod | 2 | Low | Low | Medium | 1.1.2, 1.1.3 | Azure admin | Retention policies configured | Verify policy enforcement
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.5 | Setup authentication & access | Configure service principals, RBAC for CI/CD pipelines | 3 | Medium | Medium | High | 1.1.2, 1.1.3 | Security, Azure admin | Access controls configured | Test CI/CD access
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.6 | Document artifact naming conventions | Create naming standards: myapp:v{version}-{sha} | 1 | Low | Low | Medium | 1.1.2 | Tech Lead | Naming convention doc | Team review
Phase 1: Quality Gates | 1.1 Artifact Repository | 1.1.7 | Test artifact publish/retrieve | End-to-end test of artifact lifecycle | 2 | Low | Low | High | 1.1.2-1.1.6 | DevOps | Test results doc | Successful test run
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.1 | Install Coverlet tool | Add Coverlet NuGet package to test projects | 1 | Low | Low | High | None | Developer | Coverlet installed | Test project builds
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.2 | Create coverlet.runsettings | Configure coverage collection settings, exclusions | 2 | Low | Low | Medium | 1.2.1 | Developer | runsettings file | Coverage collects correctly
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.3 | Update test projects | Add coverage collection to each test project | 4 | Medium | Low | High | 1.2.1, 1.2.2 | Developer | All test projects updated | All tests run with coverage
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.4 | Configure Azure DevOps task | Add PublishCodeCoverageResults task to pipeline | 2 | Low | Low | High | 1.2.3 | DevOps | Pipeline task configured | Coverage publishes to ADO
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.5 | Create coverage dashboard | Setup coverage dashboard in Azure DevOps | 2 | Low | Low | Medium | 1.2.4 | DevOps | Dashboard created | Dashboard shows data
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.6 | Configure branch policy - 70% threshold | Set branch policy requiring 70% line coverage | 2 | Low | Low | High | 1.2.5 | DevOps admin | Branch policy active | PR blocks if <70%
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.7 | Test coverage enforcement | Create test PR with low coverage to verify blocking | 1 | Low | Low | High | 1.2.6 | DevOps | Test results | PR blocked correctly
Phase 1: Quality Gates | 1.2 Code Coverage | 1.2.8 | Document coverage requirements | Create developer guide on coverage standards | 2 | Low | Low | Medium | 1.2.6 | Tech Lead | Coverage guide doc | Team review
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.1 | Create SonarCloud organization | Setup SonarCloud org and link to Azure DevOps | 1 | Low | Low | High | None | DevOps admin | SonarCloud org created | Org accessible
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.2 | Create project in SonarCloud | Create project for repository | 1 | Low | Low | High | 1.3.1 | DevOps admin | Project created | Project visible
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.3 | Configure quality gate | Set quality gate: A rating, 70% coverage, 0 blockers | 2 | Low | Low | High | 1.3.2 | DevOps, QA Lead | Quality gate configured | Review gate rules
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.4 | Add SonarCloudPrepare task | Add task to prepare analysis in pipeline | 2 | Low | Low | High | 1.3.2 | DevOps | Prepare task added | Task runs successfully
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.5 | Add SonarCloudAnalyze task | Add task to run code analysis | 1 | Low | Low | High | 1.3.4 | DevOps | Analyze task added | Analysis runs
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.6 | Add SonarCloudPublish task | Add task to publish results and wait for QG | 2 | Medium | Low | High | 1.3.5 | DevOps | Publish task added | Results published
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.7 | Configure branch policy | Make SonarCloud check mandatory for PRs | 1 | Low | Low | High | 1.3.6 | DevOps admin | Branch policy set | PR blocks on QG fail
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.8 | Test with failing quality gate | Test PR that fails quality gate | 1 | Low | Low | High | 1.3.7 | DevOps | Test results | PR blocked correctly
Phase 1: Quality Gates | 1.3 SonarCloud | 1.3.9 | Configure project-specific rules | Customize rules for C# projects | 3 | Medium | Low | Medium | 1.3.3 | Senior Dev, QA Lead | Custom rules configured | Rules review meeting
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.1 | Select security scanning tool | Evaluate WhiteSource, Snyk, or built-in options | 3 | Medium | Low | Medium | None | Security, DevOps | Tool selection doc | Management approval
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.2 | Setup security tool account | Create account and configure integration | 2 | Low | Low | High | 1.4.1 | Security, DevOps | Account configured | Can access portal
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.3 | Add security scan task to pipeline | Add WhiteSource or similar task | 2 | Low | Low | High | 1.4.2 | DevOps | Task added | Scan runs
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.4 | Configure vulnerability thresholds | Set to block on critical/high vulnerabilities | 2 | Medium | Medium | High | 1.4.3 | Security, DevOps | Thresholds configured | Test with known vuln
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.5 | Setup Dependabot | Enable automated dependency updates | 2 | Low | Low | Medium | None | DevOps | Dependabot enabled | PRs created for updates
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.6 | Configure credential scanning | Add CredScan task for secrets detection | 2 | Low | Low | High | None | Security, DevOps | CredScan configured | Test with dummy secret
Phase 1: Quality Gates | 1.4 Security Scanning | 1.4.7 | Document security process | Create runbook for handling security alerts | 3 | Low | Low | High | 1.4.4 | Security | Security runbook | Team training
Phase 1: Quality Gates | 1.5 Linting | 1.5.1 | Configure EditorConfig | Create .editorconfig with C# coding standards | 2 | Low | Low | Medium | None | Senior Dev | .editorconfig file | Validated in IDE
Phase 1: Quality Gates | 1.5 Linting | 1.5.2 | Setup StyleCop Analyzers | Add StyleCop.Analyzers NuGet to all projects | 3 | Low | Low | High | None | Senior Dev | StyleCop configured | Build shows warnings
Phase 1: Quality Gates | 1.5 Linting | 1.5.3 | Configure ruleset | Create custom ruleset file with team standards | 4 | Medium | Low | Medium | 1.5.2 | Senior Dev, Tech Lead | Ruleset file | Team review meeting
Phase 1: Quality Gates | 1.5 Linting | 1.5.4 | Fix existing violations | Clean up codebase to pass linting | 20 | Medium | Low | Medium | 1.5.3 | All developers | Clean codebase | Build with no warnings
Phase 1: Quality Gates | 1.5 Linting | 1.5.5 | Configure warnings as errors | Set TreatWarningsAsErrors in pipeline | 1 | Low | Low | High | 1.5.4 | DevOps | Pipeline configured | Build fails on warning
Phase 1: Quality Gates | 1.5 Linting | 1.5.6 | Setup Prettier/ESLint (if frontend) | Configure linting for TypeScript/JavaScript | 3 | Low | Low | Medium | None | Frontend Dev | Linting configured | Frontend builds clean
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.1 | Create CODEOWNERS file | Define code ownership for critical areas | 3 | Low | Low | High | None | Tech Lead | CODEOWNERS file | Test PR routing
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.2 | Configure main branch policy | Require 2 reviewers, all checks, linked work item | 2 | Low | Low | Critical | 1.2.6, 1.3.7 | DevOps admin | Main protected | Test PR to main
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.3 | Configure develop branch policy | Require 1 reviewer, all checks | 1 | Low | Low | High | 1.2.6, 1.3.7 | DevOps admin | Develop protected | Test PR to develop
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.4 | Configure release/* branch policy | Require 1-2 reviewers, all checks | 1 | Low | Low | High | 1.2.6, 1.3.7 | DevOps admin | Release/* protected | Test PR to release
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.5 | Document review process | Create PR review guidelines | 2 | Low | Low | Medium | 1.6.1-1.6.4 | Tech Lead | Review guidelines doc | Team training
Phase 1: Quality Gates | 1.6 Branch Protection | 1.6.6 | Test full protection | Create test PRs to verify all policies work | 2 | Low | Low | High | 1.6.1-1.6.4 | DevOps | Test results doc | All policies enforce
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.1 | Document current dev-6.0.0 state | Git log, pending PRs, open work | 2 | Low | Low | High | None | Tech Lead | Current state doc | Review with team
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.2 | Document current intg state | Git log, unique commits vs dev | 2 | Low | Low | High | None | Tech Lead | Intg state doc | Identify unique commits
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.3 | Document current qa state | Git log, unique commits vs intg | 2 | Low | Low | High | None | Tech Lead | QA state doc | Identify unique commits
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.4 | Document current stage state | Git log, unique commits vs qa | 2 | Low | Low | High | None | Tech Lead | Stage state doc | Identify unique commits
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.5 | Document current main state | Git log, production code | 1 | Low | Low | Critical | None | Tech Lead | Main state doc | Verified prod code
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.6 | Create branch mapping plan | Map old branches to new GitFlow structure | 3 | Medium | Medium | Critical | 2.1.1-2.1.5 | Tech Lead | Migration plan doc | Architecture review
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.7 | Identify commits to preserve | List all commits that must be migrated | 3 | Medium | Low | High | 2.1.1-2.1.5 | Tech Lead, Senior Dev | Commit list | Validate no work lost
Phase 2: Branching Migration | 2.1 Branch Mapping | 2.1.8 | Create rollback plan | Document how to rollback if issues | 2 | Low | Low | High | 2.1.6 | Tech Lead | Rollback plan doc | Review with DevOps
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.1 | Create backup tags | Tag all branches: backup-dev-6.0.0, etc | 1 | Low | Low | Critical | 2.1.8 | Tech Lead | Tags created | Verify all tags exist
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.2 | Create develop from main | git checkout -b develop from main | 1 | Low | Low | Critical | 2.2.1 | Tech Lead | Develop branch exists | Branch visible in ADO
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.3 | Merge dev-6.0.0 to develop | Merge all dev work to new develop | 2 | Medium | Medium | Critical | 2.2.2, 2.1.7 | Tech Lead | Merged successfully | All commits present
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.4 | Merge unique intg commits | Cherry-pick or merge unique intg commits | 2 | Medium | Medium | High | 2.2.3, 2.1.2 | Tech Lead | Intg work preserved | No conflicts
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.5 | Merge unique qa commits | Cherry-pick or merge unique qa commits | 2 | Medium | Medium | High | 2.2.4, 2.1.3 | Tech Lead | QA work preserved | No conflicts
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.6 | Merge unique stage commits | Cherry-pick or merge unique stage commits | 2 | Medium | Medium | High | 2.2.5, 2.1.4 | Tech Lead | Stage work preserved | No conflicts
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.7 | Create initial release branch | git checkout -b release/v6.1.0 if needed | 1 | Low | Low | Medium | 2.2.6 | Release Manager | Release branch created | Branch exists
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.8 | Verify all code present | Compare new structure to old, ensure nothing lost | 3 | Medium | Low | Critical | 2.2.2-2.2.7 | Tech Lead | Verification report | No missing commits
Phase 2: Branching Migration | 2.2 Branch Creation | 2.2.9 | Update default branch to develop | Change ADO default branch setting | 1 | Low | Low | High | 2.2.8 | DevOps admin | Default branch changed | ADO shows develop
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.1 | Create GitFlow workflow doc | Document feature/bugfix/hotfix workflows | 4 | Low | Low | High | 2.2.9 | Tech Lead | Workflow guide | Peer review
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.2 | Create Git hooks | Create pre-push hooks for branch naming | 3 | Medium | Low | Medium | 2.3.1 | Senior Dev | Git hooks scripts | Test hooks work
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.3 | Create cheat sheet | Quick reference for common operations | 2 | Low | Low | Medium | 2.3.1 | Tech Lead | Cheat sheet PDF | Team feedback
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.4 | Create training materials | Slides and demos for GitFlow training | 4 | Medium | Low | High | 2.3.1 | Tech Lead | Training materials | Dry run presentation
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.5 | Schedule training session 1 | First team training (2 hours) | 2 | Low | Low | High | 2.3.4 | Tech Lead | Session completed | Attendance >80%
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.6 | Schedule training session 2 | Second team training (2 hours) | 2 | Low | Low | High | 2.3.5 | Tech Lead | Session completed | Attendance >80%
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.7 | Create FAQ document | Common questions and answers | 3 | Low | Low | Medium | 2.3.5, 2.3.6 | Tech Lead | FAQ doc | Team adds questions
Phase 2: Branching Migration | 2.3 Developer Workflow | 2.3.8 | Update confluence/wiki | Update all documentation references | 2 | Low | Low | Medium | 2.3.1 | Tech Lead | Docs updated | Links work
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.1 | Rename dev-6.0.0 to deprecated/ | Archive old dev branch | 1 | Low | Low | High | 2.2.9, 2.3.6 | DevOps | Branch renamed | Verify rename
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.2 | Rename intg to deprecated/ | Archive old intg branch | 1 | Low | Low | High | 2.4.1 | DevOps | Branch renamed | Verify rename
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.3 | Rename qa to deprecated/ | Archive old qa branch | 1 | Low | Low | High | 2.4.2 | DevOps | Branch renamed | Verify rename
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.4 | Rename stage to deprecated/ | Archive old stage branch | 1 | Low | Low | High | 2.4.3 | DevOps | Branch renamed | Verify rename
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.5 | Monitor for old branch usage | Watch for attempts to use old branches | 5 | Low | Low | Medium | 2.4.1-2.4.4 | DevOps | Monitoring report | No usage detected
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.6 | Delete remote old branches | Delete old branches from remote after 2 weeks | 1 | Low | Low | Medium | 2.4.5 | DevOps | Branches deleted | Verify deletion
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.7 | Update pipeline triggers | Remove triggers for deprecated branches | 2 | Low | Low | High | 2.4.6 | DevOps | Pipelines updated | Test triggers work
Phase 2: Branching Migration | 2.4 Branch Decommission | 2.4.8 | Announce decommission | Send final communication to team | 1 | Low | Low | Medium | 2.4.6 | Tech Lead | Announcement sent | Team acknowledgement
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.1 | Design build pipeline architecture | Single build, artifact promotion model | 4 | Medium | Low | Critical | Phase 1 complete | DevOps, Tech Lead | Architecture diagram | Architecture review
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.2 | Design GitVersion strategy | Configure semantic versioning strategy | 3 | Medium | Low | High | 3.1.1 | DevOps | GitVersion.yml file | Test version calc
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.3 | Design deployment pipeline | Parameterized deployment with approval gates | 4 | Medium | Low | Critical | 3.1.1 | DevOps | Deployment design doc | Review with team
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.4 | Create pipeline YAML templates | Reusable templates for build/deploy | 4 | Medium | Low | High | 3.1.2, 3.1.3 | DevOps | YAML templates | Validate syntax
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.5 | Define variable groups | DEV, QA, PROD variable groups | 3 | Low | Low | High | 3.1.3 | DevOps | Variable groups created | Test variable access
Phase 3: CI/CD Transform | 3.1 Pipeline Design | 3.1.6 | Document pipeline architecture | Complete pipeline documentation | 3 | Low | Low | High | 3.1.1-3.1.5 | DevOps | Pipeline docs | Peer review
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.1 | Create build-pipeline.yml | Main build pipeline file | 3 | Medium | Low | Critical | 3.1.4 | DevOps | Pipeline YAML | Syntax validated
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.2 | Add GitVersion task | Calculate semantic version | 1 | Low | Low | High | 3.1.2, 3.2.1 | DevOps | Version calculation works | Test version output
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.3 | Add dotnet build task | Build all projects | 2 | Low | Low | Critical | 3.2.1 | DevOps | Build task configured | Solution builds
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.4 | Add unit test task | Run all unit tests with coverage | 2 | Low | Low | Critical | 3.2.3, 1.2 complete | DevOps | Test task configured | Tests run
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.5 | Add integration test task | Run integration tests | 2 | Low | Low | High | 3.2.3 | DevOps | Integration tests run | Tests pass
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.6 | Add SonarCloud tasks | Prepare, analyze, publish | 2 | Low | Low | High | 3.2.3, 1.3 complete | DevOps | SonarCloud integrated | Analysis runs
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.7 | Add security scan task | Run security scanning | 2 | Low | Low | High | 3.2.3, 1.4 complete | DevOps | Security scan runs | Scan completes
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.8 | Add Docker build task | Build Docker image | 3 | Medium | Medium | Critical | 3.2.3 | DevOps | Docker image builds | Image created
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.9 | Add Docker push task | Push image to ACR | 2 | Low | Low | Critical | 3.2.8, 1.1.2 | DevOps | Image pushed | Image in registry
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.10 | Add .dacpac build task | Build SQL project | 2 | Low | Low | Critical | 3.2.1 | DevOps | .dacpac builds | Artifact created
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.11 | Add .dacpac publish task | Publish to artifact feed | 2 | Low | Low | Critical | 3.2.10, 1.1.3 | DevOps | .dacpac published | Artifact in feed
Phase 3: CI/CD Transform | 3.2 Build Pipeline | 3.2.12 | Test build pipeline end-to-end | Full pipeline test run | 3 | Medium | Medium | Critical | 3.2.1-3.2.11 | DevOps | Pipeline passes | All artifacts created
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.1 | Create deploy-pipeline.yml | Parameterized deployment pipeline | 4 | Medium | Medium | Critical | 3.1.4, 3.1.5 | DevOps | Deploy pipeline YAML | Syntax validated
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.2 | Add artifact download tasks | Download Docker image and .dacpac | 2 | Low | Low | High | 3.3.1 | DevOps | Artifacts download | Test download
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.3 | Add database backup task | Backup DB before deployment | 3 | Medium | Low | Critical | 3.3.2 | DevOps, DB Dev | Backup task works | Backup created
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.4 | Add .dacpac deployment task | Deploy database changes | 3 | Medium | Medium | Critical | 3.3.3 | DevOps, DB Dev | DB deploys | Schema updated
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.5 | Add Kubernetes deploy task | Deploy app to K8s/AKS | 4 | Medium | Medium | Critical | 3.3.2 | DevOps | App deploys | Pods running
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.6 | Add health check task | Verify deployment health | 3 | Medium | Low | Critical | 3.3.5 | DevOps | Health checks work | App healthy
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.7 | Add smoke test task | Run critical endpoint tests | 3 | Medium | Low | High | 3.3.6 | DevOps, QA | Smoke tests run | Tests pass
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.8 | Configure approval gates | Require approvals for QA/PROD | 2 | Low | Low | High | 3.3.1 | DevOps admin | Approvals configured | Test approval flow
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.9 | Add rollback on failure | Auto-rollback if health fails | 4 | High | Medium | High | 3.3.6 | DevOps | Rollback works | Test rollback
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.10 | Add deployment notifications | Teams/Slack notifications | 2 | Low | Low | Medium | 3.3.1 | DevOps | Notifications work | Test message sent
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.11 | Test deploy to DEV | Full deployment test to DEV | 3 | Medium | Medium | Critical | 3.3.1-3.3.10 | DevOps | DEV deployment successful | App running in DEV
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.12 | Test deploy to QA | Full deployment test to QA | 3 | Medium | Medium | Critical | 3.3.11 | DevOps | QA deployment successful | App running in QA
Phase 3: CI/CD Transform | 3.3 Deploy Pipeline | 3.3.13 | Test deploy to PROD | Full deployment test to PROD | 4 | High | High | Critical | 3.3.12 | DevOps, Tech Lead | PROD deployment successful | App running in PROD
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.1 | Test BODE principle | Verify same artifact deploys everywhere | 3 | Medium | Low | Critical | 3.3.13 | DevOps, QA | BODE verified | SHA matches all envs
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.2 | Test rollback procedure | Test application rollback | 3 | Medium | Medium | Critical | 3.3.13 | DevOps | Rollback successful | Previous version runs
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.3 | Test hotfix workflow | Deploy hotfix through pipeline | 4 | Medium | Medium | Critical | 3.3.13 | DevOps, Developer | Hotfix deployed | Fix in production
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.4 | Measure pipeline performance | Time each stage, identify bottlenecks | 2 | Low | Low | Medium | 3.4.1 | DevOps | Performance report | < 30 min total
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.5 | Test concurrent builds | Multiple feature branches building | 2 | Medium | Low | Medium | 3.2.12 | DevOps | Concurrent builds work | No conflicts
Phase 3: CI/CD Transform | 3.4 Testing & Validation | 3.4.6 | Document pipeline usage | Complete user guide for developers | 4 | Low | Low | High | 3.4.1-3.4.5 | DevOps | Pipeline user guide | Team training
Phase 4: Database Strategy | 4.1 .dacpac Artifacts | 4.1.1 | Configure SQL project versioning | Add version to sqlproj | 2 | Low | Low | High | 1.1.3 | DB Developer | Version in project | Version sets correctly
Phase 4: Database Strategy | 4.1 .dacpac Artifacts | 4.1.2 | Update build to version .dacpac | Pass GitVersion to MSBuild | 2 | Medium | Low | High | 3.2.2, 4.1.1 | DevOps, DB Dev | .dacpac versioned | Version in artifact
Phase 4: Database Strategy | 4.1 .dacpac Artifacts | 4.1.3 | Test .dacpac download | Download specific version from feed | 1 | Low | Low | High | 3.2.11 | DevOps | Download works | Correct version retrieved
Phase 4: Database Strategy | 4.1 .dacpac Artifacts | 4.1.4 | Create .dacpac promotion script | Script to promote between feeds | 3 | Medium | Low | Medium | 4.1.3 | DevOps | Promotion script | Test promotion
Phase 4: Database Strategy | 4.1 .dacpac Artifacts | 4.1.5 | Document .dacpac versioning | Guide on .dacpac versioning strategy | 2 | Low | Low | Medium | 4.1.1-4.1.4 | DB Developer | Versioning doc | Team review
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.1 | Configure Azure Storage for backups | Create storage account and container | 2 | Low | Low | High | None | DevOps | Storage configured | Can write to storage
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.2 | Create backup script | PowerShell to backup database | 3 | Medium | Low | Critical | 4.2.1 | DB Developer | Backup script | Test backup
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.3 | Add backup to deploy pipeline | Backup before each deployment | 2 | Low | Low | Critical | 4.2.2, 3.3.3 | DevOps | Backup in pipeline | Backup runs
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.4 | Configure backup retention | 7/30/90 day retention by environment | 2 | Low | Low | High | 4.2.1 | DevOps | Retention configured | Old backups delete
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.5 | Create restore script | PowerShell to restore from backup | 3 | Medium | Medium | Critical | 4.2.2 | DB Developer | Restore script | Test restore
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.6 | Test restore procedure | Full restore test in DEV | 3 | Medium | Low | Critical | 4.2.5 | DB Developer | Restore successful | Data intact
Phase 4: Database Strategy | 4.2 Backup Strategy | 4.2.7 | Document backup/restore process | Complete backup/restore runbook | 3 | Low | Low | Critical | 4.2.1-4.2.6 | DB Developer | Backup runbook | Team training
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.1 | Document Expand-Contract pattern | Create guide on safe schema changes | 4 | Medium | Low | Critical | None | DB Developer, Tech Lead | Pattern guide | Team training
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.2 | Create schema change checklist | Checklist for reviewing schema PRs | 2 | Low | Low | High | 4.3.1 | DB Developer | Checklist doc | Use in PR template
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.3 | Configure SqlPackage safety flags | BlockOnPossibleDataLoss, DropObjectsNotInSource | 2 | Low | Low | High | 3.3.4 | DB Developer | Flags configured | Test blocking
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.4 | Create breaking change detector | Script to detect dangerous operations | 4 | High | Low | High | None | DB Developer | Detector script | Test detection
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.5 | Add schema validation to pipeline | Run breaking change detection | 2 | Medium | Low | High | 4.3.4 | DevOps, DB Dev | Validation in pipeline | Catches breaking changes
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.6 | Create example migrations | Show safe vs unsafe migrations | 3 | Low | Low | Medium | 4.3.1 | DB Developer | Example migrations | Team review
Phase 4: Database Strategy | 4.3 Schema Safety | 4.3.7 | Review all pending schema changes | Audit existing schema PRs for safety | 4 | Medium | Low | High | 4.3.1 | DB Developer, Tech Lead | Review complete | All PRs safe
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.1 | Create rollback decision tree | Flowchart for rollback scenarios | 3 | Low | Low | High | 4.3.1 | DB Developer, Tech Lead | Decision tree | Team review
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.2 | Test app-only rollback | Rollback app with additive schema | 2 | Low | Low | Critical | 3.4.2 | DevOps, DB Dev | Test successful | No data loss
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.3 | Test breaking change scenario | Attempt rollback with breaking schema | 3 | Medium | Medium | Critical | 4.2.6 | DB Developer | Requires DB restore | Process documented
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.4 | Measure rollback times | Time app rollback vs DB restore | 2 | Low | Low | High | 4.4.2, 4.4.3 | DevOps, DB Dev | Timing report | < 5 min app, < 30 min DB
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.5 | Create rollback runbook | Step-by-step rollback procedures | 4 | Low | Low | Critical | 4.4.1-4.4.4 | DB Developer | Rollback runbook | Team training
Phase 4: Database Strategy | 4.4 Rollback Testing | 4.4.6 | Conduct rollback drill | Practice rollback with team | 3 | Low | Low | High | 4.4.5 | All team | Drill complete | Team confident
Phase 5: Testing | 5.1 Feature Flow | 5.1.1 | Select test feature | Choose real feature to implement | 1 | Low | Low | High | All previous phases | Tech Lead | Feature selected | Feature scoped
Phase 5: Testing | 5.1 Feature Flow | 5.1.2 | Create feature branch | Branch from develop | 1 | Low | Low | High | 5.1.1 | Developer | Branch created | Branch exists
Phase 5: Testing | 5.1 Feature Flow | 5.1.3 | Implement feature with tests | Code + unit tests (>70% coverage) | 8 | Medium | Low | High | 5.1.2 | 2 Developers | Feature complete | Tests pass locally
Phase 5: Testing | 5.1 Feature Flow | 5.1.4 | Create PR to develop | Submit PR with description | 1 | Low | Low | High | 5.1.3 | Developer | PR created | PR visible
Phase 5: Testing | 5.1 Feature Flow | 5.1.5 | Verify quality gates | All checks must pass (coverage, SonarCloud, etc) | 2 | Low | Medium | Critical | 5.1.4 | Developer | All gates pass | PR mergeable
Phase 5: Testing | 5.1 Feature Flow | 5.1.6 | PR review process | Code review by peers | 2 | Low | Low | High | 5.1.5 | 2 Senior Devs | PR approved | Review comments addressed
Phase 5: Testing | 5.1 Feature Flow | 5.1.7 | Merge to develop | Complete PR merge | 1 | Low | Low | High | 5.1.6 | Developer | Merged to develop | Merge successful
Phase 5: Testing | 5.1 Feature Flow | 5.1.8 | Verify build triggers | Build pipeline runs automatically | 1 | Low | Low | Critical | 5.1.7 | DevOps | Build triggered | Build passes
Phase 5: Testing | 5.1 Feature Flow | 5.1.9 | Verify DEV deployment | Auto-deploy to DEV | 1 | Low | Low | Critical | 5.1.8 | DevOps | Deployed to DEV | Feature in DEV
Phase 5: Testing | 5.1 Feature Flow | 5.1.10 | Document developer experience | Feedback on new workflow | 2 | Low | Low | Medium | 5.1.1-5.1.9 | Developers | Experience report | Identify improvements
Phase 5: Testing | 5.2 Release Process | 5.2.1 | Create release branch | release/v6.1.0 from develop | 1 | Low | Low | High | 5.1.9 | Release Manager | Release branch created | Branch exists
Phase 5: Testing | 5.2 Release Process | 5.2.2 | Update version numbers | Version in files, changelog | 2 | Low | Low | High | 5.2.1 | Release Manager | Version updated | Version correct
Phase 5: Testing | 5.2 Release Process | 5.2.3 | Trigger release build | Build pipeline for release branch | 1 | Low | Low | High | 5.2.2 | Release Manager | Build triggered | Build passes
Phase 5: Testing | 5.2 Release Process | 5.2.4 | Deploy to QA | Deploy release to QA environment | 2 | Low | Medium | High | 5.2.3 | Release Manager | Deployed to QA | QA testing begins
Phase 5: Testing | 5.2 Release Process | 5.2.5 | QA testing cycle | Full regression testing | 16 | Medium | Medium | High | 5.2.4 | QA team | QA complete | All tests pass
Phase 5: Testing | 5.2 Release Process | 5.2.6 | Create PR release to main | PR to merge release to main | 1 | Low | Low | Critical | 5.2.5 | Release Manager | PR created | PR requires approval
Phase 5: Testing | 5.2 Release Process | 5.2.7 | Approve and merge to main | Final approval, merge to main | 1 | Low | Low | Critical | 5.2.6 | Tech Lead, Product | Merged to main | Tag created
Phase 5: Testing | 5.2 Release Process | 5.2.8 | Deploy to PROD | Production deployment | 2 | Medium | High | Critical | 5.2.7 | Release Manager | Deployed to PROD | PROD healthy
Phase 5: Testing | 5.2 Release Process | 5.2.9 | Verify BODE | Confirm same artifact in QA and PROD | 1 | Low | Low | Critical | 5.2.8 | DevOps | BODE verified | SHA matches
Phase 5: Testing | 5.2 Release Process | 5.2.10 | Merge release back to develop | Keep develop in sync | 1 | Low | Low | High | 5.2.7 | Release Manager | Merged to develop | Develop updated
Phase 5: Testing | 5.2 Release Process | 5.2.11 | Document release process | Feedback on release workflow | 2 | Low | Low | High | 5.2.1-5.2.10 | Release Manager | Process doc | Team review
Phase 5: Testing | 5.3 Hotfix Process | 5.3.1 | Simulate production bug | Create test bug scenario | 1 | Low | Low | High | 5.2.8 | Tech Lead | Bug scenario ready | Clear repro steps
Phase 5: Testing | 5.3 Hotfix Process | 5.3.2 | Create hotfix branch | hotfix/fix-login-bug from main | 1 | Low | Low | Critical | 5.3.1 | Developer | Hotfix branch created | Branch exists
Phase 5: Testing | 5.3 Hotfix Process | 5.3.3 | Implement fix with tests | Fix bug, add test | 3 | Medium | Low | Critical | 5.3.2 | Developer | Fix implemented | Tests pass
Phase 5: Testing | 5.3 Hotfix Process | 5.3.4 | Create PR to main | Fast-track PR for hotfix | 1 | Low | Low | Critical | 5.3.3 | Developer | PR created | Labeled as hotfix
Phase 5: Testing | 5.3 Hotfix Process | 5.3.5 | Expedited review | Quick review by senior dev | 1 | Low | Low | Critical | 5.3.4 | Senior Dev | PR approved | Ready to merge
Phase 5: Testing | 5.3 Hotfix Process | 5.3.6 | Merge to main | Merge hotfix to main | 1 | Low | Low | Critical | 5.3.5 | Developer | Merged to main | Tag created
Phase 5: Testing | 5.3 Hotfix Process | 5.3.7 | Deploy to PROD | Emergency production deployment | 2 | Medium | High | Critical | 5.3.6 | DevOps | Deployed to PROD | Fix verified
Phase 5: Testing | 5.3 Hotfix Process | 5.3.8 | Merge to develop | Keep develop in sync | 1 | Low | Low | High | 5.3.6 | Developer | Merged to develop | Develop updated
Phase 5: Testing | 5.3 Hotfix Process | 5.3.9 | Measure hotfix time | Total time from bug to fix | 1 | Low | Low | Critical | 5.3.1-5.3.7 | Tech Lead | Timing report | < 8 hours target
Phase 5: Testing | 5.3 Hotfix Process | 5.3.10 | Document hotfix process | Feedback and improvements | 2 | Low | Low | High | 5.3.1-5.3.9 | Tech Lead | Hotfix runbook | Emergency contacts
Phase 5: Testing | 5.4 Performance Testing | 5.4.1 | Measure build time | Time full build pipeline | 1 | Low | Low | Medium | 3.2.12 | DevOps | Build time report | < 15 min target
Phase 5: Testing | 5.4 Performance Testing | 5.4.2 | Measure deploy time to DEV | Time DEV deployment | 1 | Low | Low | Medium | 3.3.11 | DevOps | DEV deploy time | < 5 min target
Phase 5: Testing | 5.4 Performance Testing | 5.4.3 | Measure deploy time to PROD | Time PROD deployment | 1 | Low | Low | High | 5.2.8 | DevOps | PROD deploy time | < 10 min target
Phase 5: Testing | 5.4 Performance Testing | 5.4.4 | Measure rollback time | Time full rollback procedure | 1 | Low | Low | High | 4.4.2 | DevOps | Rollback time | < 5 min target
Phase 5: Testing | 5.4 Performance Testing | 5.4.5 | Test concurrent builds | 3+ feature branches building | 2 | Medium | Low | Medium | 3.2.12 | DevOps | Concurrent test results | No bottlenecks
Phase 5: Testing | 5.4 Performance Testing | 5.4.6 | Optimize slow stages | Identify and fix bottlenecks | 4 | Medium | Low | Medium | 5.4.1-5.4.5 | DevOps | Optimization complete | Improved times
Phase 5: Testing | 5.4 Performance Testing | 5.4.7 | Document performance baselines | Baseline metrics for future | 2 | Low | Low | Medium | 5.4.1-5.4.6 | DevOps | Baseline doc | Metrics tracked
Phase 6: Rollout | 6.1 Team Training | 6.1.1 | Schedule training sessions | Book rooms, send invites | 1 | Low | Low | High | Phase 5 complete | Tech Lead | Sessions scheduled | Invites sent
Phase 6: Rollout | 6.1 Team Training | 6.1.2 | Conduct training session 1 | GitFlow overview (1 hour) | 1 | Low | Low | High | 6.1.1 | Tech Lead | Session complete | Attendance recorded
Phase 6: Rollout | 6.1 Team Training | 6.1.3 | Conduct training session 2 | Hands-on workshop (2 hours) | 2 | Low | Low | High | 6.1.2 | Tech Lead, Senior Dev | Session complete | Exercises done
Phase 6: Rollout | 6.1 Team Training | 6.1.4 | Conduct training session 3 | Q&A and advanced topics (1 hour) | 1 | Low | Low | Medium | 6.1.3 | Tech Lead | Session complete | Questions answered
Phase 6: Rollout | 6.1 Team Training | 6.1.5 | Record training videos | Record sessions for future reference | 2 | Low | Low | Medium | 6.1.2-6.1.4 | Tech Lead | Videos uploaded | Videos accessible
Phase 6: Rollout | 6.1 Team Training | 6.1.6 | Gather training feedback | Survey on training effectiveness | 1 | Low | Low | Medium | 6.1.2-6.1.4 | Tech Lead | Feedback collected | Improvement areas identified
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.1 | Select pilot team | Choose 1-2 teams for pilot | 1 | Low | Low | High | 6.1.6 | Tech Lead | Pilot teams selected | Teams committed
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.2 | Migrate pilot repositories | Migrate pilot team repos to GitFlow | 4 | Medium | Medium | High | 6.2.1 | DevOps, Tech Lead | Repos migrated | New workflow active
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.3 | Week 1 daily check-ins | Daily support for pilot team | 5 | Low | Low | High | 6.2.2 | Tech Lead | Check-ins complete | Issues resolved
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.4 | Gather pilot feedback | Collect feedback from pilot team | 2 | Low | Low | High | 6.2.3 | Tech Lead | Feedback collected | Improvement list
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.5 | Refine processes | Update docs based on feedback | 3 | Low | Low | High | 6.2.4 | Tech Lead | Updates complete | Docs improved
Phase 6: Rollout | 6.2 Pilot Rollout | 6.2.6 | Go/no-go decision | Decision to proceed with full rollout | 1 | Low | Low | Critical | 6.2.5 | Tech Lead, Management | Decision made | Approval to proceed
Phase 6: Rollout | 6.3 Full Rollout | 6.3.1 | Create rollout schedule | Plan team-by-team migration | 2 | Low | Low | High | 6.2.6 | Tech Lead | Schedule created | Teams notified
Phase 6: Rollout | 6.3 Full Rollout | 6.3.2 | Migrate Team A | Full migration for Team A | 4 | Medium | Medium | High | 6.3.1 | DevOps, Tech Lead | Team A migrated | Team productive
Phase 6: Rollout | 6.3 Full Rollout | 6.3.3 | Migrate Team B | Full migration for Team B | 4 | Medium | Medium | High | 6.3.2 | DevOps, Tech Lead | Team B migrated | Team productive
Phase 6: Rollout | 6.3 Full Rollout | 6.3.4 | Migrate Team C | Full migration for Team C | 4 | Medium | Medium | High | 6.3.3 | DevOps, Tech Lead | Team C migrated | Team productive
Phase 6: Rollout | 6.3 Full Rollout | 6.3.5 | Migrate remaining teams | Migrate all remaining teams | 8 | Medium | Medium | High | 6.3.4 | DevOps, Tech Lead | All teams migrated | Everyone on GitFlow
Phase 6: Rollout | 6.3 Full Rollout | 6.3.6 | Monitor for issues | 2-week monitoring period | 10 | Low | Low | High | 6.3.5 | DevOps, Tech Lead | Monitoring complete | Stable operation
Phase 6: Rollout | 6.4 Decommissioning | 6.4.1 | Final branch cleanup | Delete all deprecated branches | 2 | Low | Low | Medium | 6.3.6 | DevOps | Branches deleted | Verified deletion
Phase 6: Rollout | 6.4 Decommissioning | 6.4.2 | Archive old pipelines | Disable old environment pipelines | 2 | Low | Low | High | 6.3.6 | DevOps | Pipelines archived | No old triggers
Phase 6: Rollout | 6.4 Decommissioning | 6.4.3 | Update all documentation | Final documentation updates | 4 | Low | Low | High | 6.3.6 | Tech Lead | Docs updated | All links work
Phase 6: Rollout | 6.4 Decommissioning | 6.4.4 | Announce completion | Company-wide success announcement | 1 | Low | Low | Medium | 6.4.1-6.4.3 | Tech Lead | Announcement sent | Celebrate success!
Phase 6: Rollout | 6.4 Decommissioning | 6.4.5 | Measure final metrics | Compare before/after metrics | 3 | Low | Low | High | 6.3.6 | Tech Lead | Metrics report | Show improvements
Phase 6: Rollout | 6.4 Decommissioning | 6.4.6 | Conduct retrospective | Team retrospective on migration | 2 | Low | Low | High | 6.4.5 | Tech Lead | Retro complete | Lessons documented
Phase 6: Rollout | 6.4 Decommissioning | 6.4.7 | Create case study | Document migration for future reference | 4 | Low | Low | Low | 6.4.6 | Tech Lead | Case study | Knowledge preserved