## Summary
GitFlow Migration - Consolidated Task Summary
Consolidation: 316 original tasks → 99 consolidated tasks (~14 per phase)
Phase | Original Tasks | Consolidated Tasks | Total Hours
Phase 1: Quality Gates | 69 | 15 | 238
Phase 2: Branching Migration | 46 | 15 | 98
Phase 3: CI/CD Transform | 46 | 14 | 126
Phase 4: Database Strategy | 24 | 12 | 56
Phase 5: Testing & Validation | 52 | 15 | 96
Phase 6: Rollout | 41 | 15 | 157
Special: Feature Flags | 38 | 13 | 131
TOTAL | 316 | 99 | 902

## GitFlow Migration Tasks
Phase | Sub-Phase | Task ID | Task Name | Task Description | Hours | Complexity | Risk Level | Criticality | Prerequisites | Skills Required | Deliverable | Validation Required
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | P1.1 | 1.1 ACR & Artifact Repo Setup (Consolidated) | Combined tasks: Configure ACR retention policy; Setup ACR geo-replication (optional); Configure Artifact Feed retention | 7 | Medium | Low | Low | ACR already exists | Azure admin, DevOps | Combined: Geo-replication enabled, Retention configured, Retention policy configured | No
Phase 1: Quality Gates | 1.1 ACR & Artifact Repo Setup | P1.2 | 1.1 ACR & Artifact Repo Setup (Consolidated) | Combined tasks: Document artifact versioning strategy; Test ACR artifact retrieval; Test Artifact Feed retrieval | 6 | Low | Low | High | None | DevOps, Tech Lead | Combined: Versioning doc, Test results | No
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | P1.3 | 1.2 API Versioning & BODE Prep (Consolidated) | Combined tasks: Review API containerization; Implement GitVersion for APIs; Tag API images with version+SHA | 7 | Medium | Low | High | APIs containerized | DevOps | Combined: GitVersion configured, API inventory, Images tagged correctly | No
Phase 1: Quality Gates | 1.2 API Versioning & BODE Prep | P1.4 | 1.2 API Versioning & BODE Prep (Consolidated) | Combined tasks: Test API BODE deployment; Document API BODE process | 5 | Medium | Medium | Medium | 1.2.3 | DevOps | Combined: API BODE doc, BODE verified for APIs | No
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | P1.5 | 1.3 Web App BODE Preparation (Consolidated) | Combined tasks: Audit Web app configurations; Separate .env from build artifacts; Create config replacement script | 14 | Medium | Medium | High | None | DevOps, Frontend Dev | Combined: Config externalized, Replacement script, Config inventory | No
Phase 1: Quality Gates | 1.3 Web App BODE Preparation | P1.6 | 1.3 Web App BODE Preparation (Consolidated) | Combined tasks: Update Web build pipeline; Test Web BODE deployment; Document Web BODE process | 11 | Medium | Medium | Medium | 1.3.2 | DevOps, Frontend Dev | Combined: Pipeline updated, Web BODE doc, BODE verified for Web | No
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | P1.7 | 1.4 Mobile App BODE Preparation (Consolidated) | Combined tasks: Audit Mobile app configurations; Separate config from build; Implement runtime config loading | 18 | Medium | Medium | High | None | DevOps, Mobile Dev | Combined: Runtime config works, Config externalized, Config inventory | No
Phase 1: Quality Gates | 1.4 Mobile App BODE Preparation | P1.8 | 1.4 Mobile App BODE Preparation (Consolidated) | Combined tasks: Update Mobile build pipeline; Test Mobile BODE deployment; Document Mobile BODE process | 13 | Medium | Medium | Medium | 1.4.3 | DevOps, Mobile Dev, QA | Combined: Pipeline updated, BODE verified for Mobile, Mobile BODE doc | No
Phase 1: Quality Gates | 1.5 Code Coverage Gates | P1.9 | 1.5 Code Coverage Gates (Consolidated) | Combined tasks: Audit current test coverage; Install Coverlet in test projects; Create coverlet.runsettings; +2 more | 11 | Low | Low | Medium | None | DevOps, Developer, Developers, QA Lead | Combined: Coverlet installed, runsettings file, Coverage baseline report | No
Phase 1: Quality Gates | 1.5 Code Coverage Gates | P1.10 | 1.5 Code Coverage Gates (Consolidated) | Combined tasks: Set 70% coverage threshold; Increase test coverage (if needed); Configure branch policies; +1 more | 24 | Medium | Low | High | 1.5.4 | All Developers, DevOps, DevOps admin | Combined: Threshold enforced, Branch policy set, 70% coverage achieved | No
Phase 1: Quality Gates | 1.6 Linting Implementation | P1.11 | 1.6 Linting Implementation (Consolidated) | Combined tasks: Configure EditorConfig; Add StyleCop Analyzers; Create custom ruleset; +1 more | 33 | Medium | Low | Medium | None | All Developers, Senior Dev, Tech Lead | Combined: StyleCop installed, Ruleset file, .editorconfig file | No
Phase 1: Quality Gates | 1.6 Linting Implementation | P1.12 | 1.6 Linting Implementation (Consolidated) | Combined tasks: Add linting to Azure Pipelines; Setup frontend linting (if applicable); Configure pre-commit hooks; +1 more | 9 | Low | Low | Medium | 1.6.4 | DevOps, Frontend Dev, Senior Dev | Combined: Pre-commit hooks, Linting in pipeline, Frontend linting | No
Phase 1: Quality Gates | 1.7 SonarQube/SonarCloud Setup | P1.13 | 1.7 SonarQube/SonarCloud Setup (Consolidated) | Combined tasks: Decide SonarQube vs SonarCloud; Create SonarCloud org (if cloud); Create projects in SonarCloud; +7 more | 21 | Medium | Low | Medium | None | DevOps, DevOps admin, QA Lead, Senior Dev, Tech Lead | Combined: Decision made, Projects created, Org created | No
Phase 1: Quality Gates | 1.8 SAST Scanning | P1.14 | 1.8 SAST Scanning (Consolidated) | Combined tasks: Select SAST tool; Setup SAST tool account; Configure SAST scan in pipeline; +7 more | 43 | Medium | Medium | Medium | None | DevOps, Developers, Security, Tech Lead | Combined: SAST in pipeline, Account setup, Tool selected | No
Phase 1: Quality Gates | 1.9 Branch Protection Policies | P1.15 | 1.9 Branch Protection Policies (Consolidated) | Combined tasks: Create CODEOWNERS file; Configure main branch protection; Configure develop branch protection; +6 more | 16 | Low | Low | Medium | None | DevOps, DevOps admin, Tech Lead | Combined: Develop protected, Main protected, CODEOWNERS file | No
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | P2.1 | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Document current branch structure; Analyze dev-6.0.0 commits; Analyze intg commits | 9 | Medium | Low | High | Phase 1 complete | Tech Lead | Combined: Current structure doc, Dev analysis doc, Intg analysis doc | No
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | P2.2 | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Analyze qa commits; Analyze stage commits; Analyze main (prod) state | 8 | Medium | Low | High | 2.1.3 | Tech Lead | Combined: QA analysis doc, Stage analysis doc, Main state doc | No
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | P2.3 | 2.1 Branch Mapping & Analysis (Consolidated) | Combined tasks: Create GitFlow mapping plan; Identify work to preserve; Create rollback plan | 10 | Medium | Medium | High | 2.1.2-2.1.6 | DevOps, Senior Dev, Tech Lead | Combined: Rollback plan, Preservation checklist, Migration plan doc | No
Phase 2: Branching Migration | 2.1 Branch Mapping & Analysis | P2.4 | Get migration approval | Present plan to leadership | 2 | Low | Low | Critical | 2.1.7-2.1.9 | Tech Lead | Approval received | Green light to proceed
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | P2.5 | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Announce code freeze; Create backup tags; Export current branch state; +1 more | 4 | Low | Low | High | 2.1.10 | Tech Lead | Combined: State exported, Announcement sent, Backup tags created | No
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | P2.6 | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Merge dev-6.0.0 to develop; Cherry-pick unique intg commits; Cherry-pick unique qa commits; +1 more | 9 | Medium | Medium | High | 2.2.4, 2.1.8 | Tech Lead | Combined: Intg work preserved, QA work preserved, Dev work in develop | No
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | P2.7 | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Verify all work preserved; Create initial release branch (if needed); Set develop as default branch; +1 more | 6 | Low | Medium | Medium | 2.2.8 | DevOps admin, Release Manager, Senior Dev, Tech Lead | Combined: Default changed, Release branch created, Verification passed | No
Phase 2: Branching Migration | 2.2 New Branch Structure Creation | P2.8 | 2.2 New Branch Structure Creation (Consolidated) | Combined tasks: Apply branch protection policies; Test new branch structure | 3 | Low | Low | Critical | 2.2.12, 1.9 complete | DevOps admin, Developer | Combined: Policies applied, Test successful | No
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | P2.9 | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Create GitFlow overview document; Document feature branch workflow; Document bugfix workflow; +1 more | 11 | Low | Low | High | 2.2.14 | Release Mgr, Tech Lead | Combined: Overview doc, Bugfix workflow doc, Feature workflow doc | No
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | P2.10 | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Document hotfix workflow; Create Git command cheat sheet; Create visual flow diagrams; +1 more | 10 | Low | Low | Medium | 2.3.1 | Tech Lead | Combined: Cheat sheet, Hotfix workflow doc, Flow diagrams | No
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | P2.11 | 2.3 Developer Workflow Documentation (Consolidated) | Combined tasks: Create commit message guidelines; Create FAQ document; Setup Git hooks for branch naming; +1 more | 10 | Medium | Low | Medium | None | Senior Dev, Tech Lead | Combined: Git hooks ready, FAQ doc, Commit guidelines | No
Phase 2: Branching Migration | 2.3 Developer Workflow Documentation | P2.12 | Update Confluence/Wiki | Update all documentation links | 2 | Low | Low | Medium | 2.3.1-2.3.12 | Tech Lead | Wiki updated | All links work
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | P2.13 | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Rename dev-6.0.0 to deprecated/; Rename intg to deprecated/; Rename qa to deprecated/ | 3 | Low | Low | High | 2.2.14 | DevOps | Combined: Branch renamed | No
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | P2.14 | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Rename stage to deprecated/; Update pipeline triggers; Communicate branch deprecation | 4 | Low | Low | Medium | 2.4.3 | DevOps, Tech Lead | Combined: Branch renamed, Pipelines updated, Communication sent | No
Phase 2: Branching Migration | 2.4 Old Branch Decommissioning | P2.15 | 2.4 Old Branch Decommissioning (Consolidated) | Combined tasks: Monitor for old branch usage; Delete remote deprecated branches; Document decommissioning | 7 | Low | Low | Medium | 2.4.6 | DevOps | Combined: Decommission doc, Branches deleted, No usage detected | No
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | P3.1 | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Design build pipeline architecture; Create build-pipeline.yml; Add trigger configuration; +1 more | 12 | Medium | Low | High | Phase 2 complete | DevOps, Tech Lead | Combined: Build YAML created, Triggers configured, Architecture doc | No
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | P3.2 | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add build stage; Add unit test stage; Add integration test stage; +1 more | 7 | Low | Low | High | 3.1.2 | DevOps | Combined: Unit test stage, Build stage added, Integration test stage | No
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | P3.3 | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add SonarCloud stages; Add SAST scan stage; Add Docker build stage; +1 more | 9 | Medium | Low | High | 3.1.5, 1.7 complete | DevOps | Combined: Docker build stage, SAST stage, SonarCloud stages | No
Phase 3: CI/CD Transform | 3.1 Build Pipeline Design & YAML | P3.4 | 3.1 Build Pipeline Design & YAML (Consolidated) | Combined tasks: Add .dacpac build stage; Add .dacpac publish stage; Test build pipeline end-to-end | 8 | Medium | Medium | Critical | 3.1.2 | DevOps | Combined: .dacpac publish stage, .dacpac build stage, Build pipeline works | No
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | P3.5 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Design deployment architecture; Create deploy-pipeline.yml; Add environment parameters; +2 more | 15 | Medium | Medium | High | 3.1.15 | DevOps, Tech Lead | Combined: Deploy architecture doc, Deploy YAML created, Parameters added | No
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | P3.6 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Add .dacpac download stage; Add database backup stage; Add .dacpac deployment stage; +2 more | 15 | Medium | Medium | High | 3.2.4, 1.1.6 | DB Dev, DevOps | Combined: Backup stage added, .dacpac deploy stage, .dacpac download works | No
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | P3.7 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Add health check stage; Add smoke test stage; Add approval gates; +2 more | 14 | Medium | Medium | Low | 3.2.9 | DevOps, DevOps admin, QA | Combined: Approvals configured, Smoke test stage, Health check stage | No
Phase 3: CI/CD Transform | 3.2 Deploy Pipeline Design & YAML | P3.8 | 3.2 Deploy Pipeline Design & YAML (Consolidated) | Combined tasks: Test deploy pipeline to DEV; Test deploy pipeline to QA; Test deploy pipeline to STG; +1 more | 14 | Medium | Medium | High | 3.2.2-3.2.15 | DevOps, Tech Lead | Combined: QA deploy successful, STG deploy successful, DEV deploy successful | No
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | P3.9 | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Create service principals for pipelines; Configure Key Vault integration | 6 | Medium | Medium | High | None | DevOps, Security | Combined: SPs created, Key Vault configured | No
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | P3.10 | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Setup RBAC for environments; Configure pipeline permissions | 5 | Medium | Medium | High | 3.3.1 | DevOps, DevOps admin, Security | Combined: RBAC configured, Permissions set | No
Phase 3: CI/CD Transform | 3.3 Security & Access Setup | P3.11 | 3.3 Security & Access Setup (Consolidated) | Combined tasks: Test security configuration; Document security setup | 4 | Medium | Low | High | 3.3.1-3.3.4 | DevOps, Security | Combined: Security doc, Security tested | No
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | P3.12 | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Document build pipeline; Document deployment pipeline | 7 | Low | Low | High | 3.1.15 | DevOps | Combined: Build pipeline doc, Deploy pipeline doc | No
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | P3.13 | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Document artifact selection; Create pipeline troubleshooting guide | 5 | Low | Low | Medium | 3.2.4 | DevOps | Combined: Troubleshooting guide, Artifact selection doc | No
Phase 3: CI/CD Transform | 3.4 Pipeline Documentation | P3.14 | 3.4 Pipeline Documentation (Consolidated) | Combined tasks: Create pipeline architecture diagrams; Document environment variables | 5 | Low | Low | Medium | 3.1.1, 3.2.1 | DevOps | Combined: Architecture diagrams, Env var documentation | No
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | P4.1 | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Verify .dacpac artifact feed exists; Create .dacpac artifact feed (if needed) | 3 | Low | Low | High | 1.1.3 | DevOps | Combined: Status verified, Feed created | No
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | P4.2 | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Configure .dacpac versioning; Test .dacpac publish | 4 | Low | Low | High | 3.1.4, 4.1.1 | DB Dev, DevOps | Combined: Publish tested, Versioning works | No
Phase 4: Database Strategy | 4.1 .dacpac Artifact Management | P4.3 | 4.1 .dacpac Artifact Management (Consolidated) | Combined tasks: Test .dacpac download; Document .dacpac artifact strategy | 4 | Low | Low | Medium | 4.1.4 | DB Dev, DevOps | Combined: .dacpac strategy doc, Download tested | No
Phase 4: Database Strategy | 4.2 Database Backup & Restore | P4.4 | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Verify Azure Storage exists; Create backup storage (if needed) | 3 | Low | Low | High | None | DevOps | Combined: Storage created, Storage verified | No
Phase 4: Database Strategy | 4.2 Database Backup & Restore | P4.5 | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Create backup script; Integrate backup into deploy pipeline | 5 | Medium | Low | Critical | 4.2.2 | DB Developer, DevOps | Combined: Backup in pipeline, Backup script | No
Phase 4: Database Strategy | 4.2 Database Backup & Restore | P4.6 | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Configure backup retention; Create restore script | 5 | Medium | Medium | High | 4.2.2 | DB Developer, DevOps | Combined: Retention configured, Restore script | No
Phase 4: Database Strategy | 4.2 Database Backup & Restore | P4.7 | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Test backup in DEV; Test restore in DEV | 5 | Medium | Low | High | 4.2.4 | DB Dev, DB Developer, DevOps | Combined: Restore tested, Backup tested | No
Phase 4: Database Strategy | 4.2 Database Backup & Restore | P4.8 | 4.2 Database Backup & Restore (Consolidated) | Combined tasks: Document backup/restore process; Train team on backup/restore | 5 | Low | Low | High | 4.2.3-4.2.8 | DB Developer | Combined: Backup runbook, Team trained | No
Phase 4: Database Strategy | 4.3 Rollback Testing | P4.9 | 4.3 Rollback Testing (Consolidated) | Combined tasks: Create rollback decision tree; Test app-only rollback | 5 | Low | Low | High | None | DB Dev, DB Developer, DevOps, Tech Lead | Combined: App rollback tested, Decision tree | No
Phase 4: Database Strategy | 4.3 Rollback Testing | P4.10 | 4.3 Rollback Testing (Consolidated) | Combined tasks: Test app + additive schema rollback; Test breaking schema scenario | 6 | Medium | Medium | High | 4.2.8 | DB Developer | Combined: Additive rollback tested, Breaking scenario tested | No
Phase 4: Database Strategy | 4.3 Rollback Testing | P4.11 | 4.3 Rollback Testing (Consolidated) | Combined tasks: Measure rollback times; Create rollback runbook | 6 | Low | Low | High | 4.3.2-4.3.4 | DB Dev, DB Developer, DevOps | Combined: Timing report, Rollback runbook | No
Phase 4: Database Strategy | 4.3 Rollback Testing | P4.12 | 4.3 Rollback Testing (Consolidated) | Combined tasks: Conduct rollback drill; Document lessons learned | 5 | Low | Low | Medium | 4.3.6 | All team, DB Developer | Combined: Lessons doc, Drill completed | No
Phase 5: Testing & Validation | 5.1 Development Branch Testing | P5.1 | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Create test feature branch; Implement test feature; Create PR to develop; +1 more | 8 | Low | Medium | High | Phase 3, 4 complete | DevOps, Developer | Combined: Feature implemented, Branch created, PR created | No
Phase 5: Testing & Validation | 5.1 Development Branch Testing | P5.2 | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Verify branch protection works; Complete PR review and merge; Verify build triggers on merge; +1 more | 5 | Low | Low | High | 5.1.4 | DevOps, Developer, Senior Dev | Combined: Protection verified, Build triggered, PR merged | No
Phase 5: Testing & Validation | 5.1 Development Branch Testing | P5.3 | 5.1 Development Branch Testing (Consolidated) | Combined tasks: Verify artifact versioning; Document dev branch test results | 3 | Low | Low | High | 5.1.8 | DevOps | Combined: Versions verified, Test report | No
Phase 5: Testing & Validation | 5.2 Release Branch Testing | P5.4 | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Create test release branch; Update version in release; Trigger release build; +2 more | 7 | Low | Medium | High | 5.1.10 | DevOps, Release Manager | Combined: Release created, Build triggered, Version updated | No
Phase 5: Testing & Validation | 5.2 Release Branch Testing | P5.5 | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Verify artifact selection works; Test QA approval gate; Deploy release to STG; +2 more | 7 | Low | Medium | High | 5.2.5 | DevOps, Release Manager, Tech Lead | Combined: Artifact verified, Approval tested, Deployed to STG | No
Phase 5: Testing & Validation | 5.2 Release Branch Testing | P5.6 | 5.2 Release Branch Testing (Consolidated) | Combined tasks: Deploy to PROD; Verify BODE in release; Merge release back to develop; +1 more | 8 | Medium | Low | High | 5.2.10 | DevOps, Release Manager | Combined: Deployed to PROD, BODE verified, Merged to develop | No
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | P5.7 | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Simulate production bug; Create hotfix branch; Implement hotfix; +1 more | 5 | Low | Low | High | 5.2.14 | Developer, Tech Lead | Combined: Hotfix created, Bug scenario ready, Fix implemented | No
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | P5.8 | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Expedited review; Merge hotfix to main; Verify hotfix build; +1 more | 5 | Medium | Low | Critical | 5.3.4 | DevOps, Developer, Senior Dev | Combined: Build successful, Merged to main, PR approved | No
Phase 5: Testing & Validation | 5.3 Hotfix Branch Testing | P5.9 | 5.3 Hotfix Branch Testing (Consolidated) | Combined tasks: Verify hotfix works; Merge hotfix to develop; Measure hotfix time; +1 more | 5 | Low | Low | High | 5.3.8 | Developer, QA, Tech Lead | Combined: Time measured, Fix verified, Merged to develop | No
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | P5.10 | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Measure build pipeline time; Measure deploy to DEV time; Measure deploy to QA time; +1 more | 5 | Low | Low | Medium | 5.1.10 | DevOps | Combined: DEV deploy time, Build time measured, QA deploy time | No
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | P5.11 | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Test concurrent feature builds; Measure rollback time; Measure DB restore time; +1 more | 10 | Medium | Low | Medium | 5.1.10 | DB Developer, DevOps | Combined: Rollback time measured, Restore time measured, Concurrent test done | No
Phase 5: Testing & Validation | 5.4 Performance & Load Testing | P5.12 | 5.4 Performance & Load Testing (Consolidated) | Combined tasks: Identify bottlenecks; Optimize slow stages; Document performance baselines | 13 | Medium | Low | Medium | 5.4.1-5.4.8 | DevOps | Combined: Optimizations complete, Baseline doc, Bottlenecks identified | No
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | P5.13 | 5.5 Rollback Scenario Testing (Consolidated) | Combined tasks: Test rollback scenario 1; Test rollback scenario 2 | 5 | Medium | Low | Critical | 4.3.2 | DB Dev, DevOps | Combined: Scenario 2 tested, Scenario 1 tested | No
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | P5.14 | 5.5 Rollback Scenario Testing (Consolidated) | Combined tasks: Test rollback scenario 3; Test rollback scenario 4 | 7 | Medium | Medium | High | 4.3.4 | DB Dev, DB Developer, DevOps | Combined: Scenario 3 tested, Scenario 4 tested | No
Phase 5: Testing & Validation | 5.5 Rollback Scenario Testing | P5.15 | Document all rollback scenarios | Complete rollback matrix | 3 | Low | Low | Critical | 5.5.1-5.5.4 | Tech Lead | Rollback matrix | All scenarios documented
Phase 6: Rollout | 6.1 Documentation Preparation | P6.1 | 6.1 Documentation Preparation (Consolidated) | Combined tasks: Consolidate all documentation; Create quick start guide; Create video tutorials | 12 | Medium | Low | Medium | Phase 5 complete | Tech Lead | Combined: Quick start guide, Tutorial videos, Docs consolidated | No
Phase 6: Rollout | 6.1 Documentation Preparation | P6.2 | 6.1 Documentation Preparation (Consolidated) | Combined tasks: Create FAQ document; Update Confluence/Wiki; Create training slides | 11 | Low | Low | High | 6.1.1 | Tech Lead | Combined: Wiki updated, Training slides, FAQ doc | No
Phase 6: Rollout | 6.1 Documentation Preparation | P6.3 | Share documentation links | Send to all developers | 1 | Low | Low | High | 6.1.5 | Tech Lead | Links shared | Team has access
Phase 6: Rollout | 6.2 Team Training | P6.4 | 6.2 Team Training (Consolidated) | Combined tasks: Schedule training sessions; Conduct training session 1 | 4 | Low | Low | High | 6.1.7 | Tech Lead | Combined: Session 1 complete, Sessions scheduled | No
Phase 6: Rollout | 6.2 Team Training | P6.5 | 6.2 Team Training (Consolidated) | Combined tasks: Conduct training session 2; Conduct hands-on workshop | 4 | Low | Low | High | 6.2.2 | DevOps, Senior Dev, Tech Lead | Combined: Session 2 complete, Workshop complete | No
Phase 6: Rollout | 6.2 Team Training | P6.6 | 6.2 Team Training (Consolidated) | Combined tasks: Office hours - Week 1; Gather training feedback | 6 | Low | Low | Medium | 6.2.4 | Tech Lead | Combined: Office hours done, Feedback collected | No
Phase 6: Rollout | 6.3 Pilot Team Rollout | P6.7 | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Select pilot team; Pilot team kickoff; Migrate pilot repositories | 6 | Medium | Medium | High | 6.2.6 | DevOps, Tech Lead | Combined: Pilot team selected, Kickoff complete, Repos migrated | No
Phase 6: Rollout | 6.3 Pilot Team Rollout | P6.8 | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Shadow pilot team - Day 1; Shadow pilot team - Week 1; Gather pilot feedback | 20 | Low | Low | High | 6.3.3 | DevOps, Tech Lead | Combined: Week 1 complete, Feedback collected, Day 1 support done | No
Phase 6: Rollout | 6.3 Pilot Team Rollout | P6.9 | 6.3 Pilot Team Rollout (Consolidated) | Combined tasks: Address pilot issues; Update documentation from pilot; Pilot go/no-go decision | 12 | Medium | Low | High | 6.3.6 | DevOps, Management, Tech Lead | Combined: Docs updated, Decision made, Issues resolved | No
Phase 6: Rollout | 6.4 Full Team Rollout | P6.10 | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Create rollout schedule; Migrate Team A; Support Team A - Week 1 | 13 | Medium | Medium | High | 6.3.9 | DevOps, Tech Lead | Combined: Team A support done, Schedule created, Team A migrated | No
Phase 6: Rollout | 6.4 Full Team Rollout | P6.11 | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Migrate Team B; Support Team B - Week 1; Migrate Team C | 17 | Medium | Medium | High | 6.4.2 | DevOps, Tech Lead | Combined: Team B migrated, Team B support done, Team C migrated | No
Phase 6: Rollout | 6.4 Full Team Rollout | P6.12 | 6.4 Full Team Rollout (Consolidated) | Combined tasks: Support Team C - Week 1; Migrate remaining teams; Extended support period | 27 | Medium | Medium | High | 6.4.6 | DevOps, Tech Lead | Combined: Support period complete, All teams migrated, Team C support done | No
Phase 6: Rollout | 6.5 Old Process Decommissioning | P6.13 | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Verify all teams migrated; Archive old pipeline definitions; Disable old pipelines; +1 more | 7 | Low | Low | Medium | 6.4.9 | DevOps, Tech Lead | Combined: All teams confirmed, Pipelines archived, Old pipelines disabled | No
Phase 6: Rollout | 6.5 Old Process Decommissioning | P6.14 | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Archive old documentation; Update all wiki links; Announce completion; +1 more | 10 | Low | Low | Medium | 6.5.1 | Tech Lead | Combined: Announcement sent, Docs archived, Links updated | No
Phase 6: Rollout | 6.5 Old Process Decommissioning | P6.15 | 6.5 Old Process Decommissioning (Consolidated) | Combined tasks: Conduct retrospective; Create case study | 7 | Low | Low | Low | 6.5.8 | Tech Lead | Combined: Retro complete, Case study | No
Special: Feature Flags | FF.1 Tool Selection & Setup | SP.1 | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Evaluate LaunchDarkly; Evaluate Split.io; Compare LaunchDarkly vs Split.io | 11 | Medium | Low | High | None | Senior Dev, Tech Lead | Combined: Comparison doc, Evaluation report | No
Special: Feature Flags | FF.1 Tool Selection & Setup | SP.2 | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Get budget approval; Create tool account; Create projects in tool | 6 | Low | Low | High | FF.1.3 | DevOps, Management, Tech Lead | Combined: Projects created, Account created, Budget approved | No
Special: Feature Flags | FF.1 Tool Selection & Setup | SP.3 | FF.1 Tool Selection & Setup (Consolidated) | Combined tasks: Configure environments; Setup SDK keys; Configure access controls | 6 | Low | Low | High | FF.1.6 | DevOps, Security | Combined: SDK keys generated, Environments configured, Access controls set | No
Special: Feature Flags | FF.2 C# Adapter Development | SP.4 | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Design adapter architecture; Create IFeatureFlagProvider interface; Implement LaunchDarkly adapter | 15 | Medium | Low | High | FF.1.5 | Senior Dev, Tech Lead | Combined: Interface created, LD adapter complete, Architecture doc | No
Special: Feature Flags | FF.2 C# Adapter Development | SP.5 | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Implement Split.io adapter (optional); Implement InMemory adapter; Create FeatureFlagContext class | 14 | Medium | Low | Medium | FF.2.2 | Senior Dev | Combined: Split adapter complete, InMemory adapter complete, Context class created | No
Special: Feature Flags | FF.2 C# Adapter Development | SP.6 | FF.2 C# Adapter Development (Consolidated) | Combined tasks: Implement DI configuration; Create helper extensions; Write unit tests for adapter | 13 | Medium | Low | Medium | FF.2.3-FF.2.5 | Senior Dev | Combined: DI configured, Tests written, Extensions created | No
Special: Feature Flags | FF.2 C# Adapter Development | SP.7 | Document adapter usage | Developer guide on using adapter | 4 | Low | Low | High | FF.2.9 | Senior Dev | Adapter guide | Clear examples
Special: Feature Flags | FF.3 Integration & Testing | SP.8 | FF.3 Integration & Testing (Consolidated) | Combined tasks: Add adapter to API projects; Add adapter to Web projects; Add adapter to Mobile projects (if applicable) | 14 | Medium | Medium | Medium | FF.2.10 | Developers, Frontend Devs, Mobile Devs | Combined: Mobile integrated, APIs integrated, Web integrated | No
Special: Feature Flags | FF.3 Integration & Testing | SP.9 | FF.3 Integration & Testing (Consolidated) | Combined tasks: Create test feature flags; Test flag evaluation; Test flag targeting | 8 | Medium | Low | High | FF.3.1-FF.3.3 | DevOps, Developers | Combined: Test flags created, Targeting tested, Evaluation tested | No
Special: Feature Flags | FF.3 Integration & Testing | SP.10 | FF.3 Integration & Testing (Consolidated) | Combined tasks: Test flag in all environments; Test adapter switching; Performance test flag evaluation | 9 | Medium | Low | Medium | FF.3.5 | DevOps, Developers, Senior Dev | Combined: All envs tested, Switching tested, Performance tested | No
Special: Feature Flags | FF.4 Documentation & Training | SP.11 | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create feature flag overview doc; Create flag lifecycle guide; Create flag naming conventions; +1 more | 13 | Low | Low | High | FF.2.10 | Senior Dev, Tech Lead | Combined: Overview doc, Lifecycle guide, Naming guide | No
Special: Feature Flags | FF.4 Documentation & Training | SP.12 | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create LaunchDarkly portal guide; Create code examples; Create training presentation; +1 more | 13 | Low | Low | Medium | FF.1.7 | DevOps, Senior Dev, Tech Lead | Combined: Training slides, Code examples, Portal guide | No
Special: Feature Flags | FF.4 Documentation & Training | SP.13 | FF.4 Documentation & Training (Consolidated) | Combined tasks: Create FAQ for feature flags; Publish all flag documentation | 5 | Low | Low | Medium | FF.4.8 | Tech Lead | Combined: Flag FAQ, Docs published | No